## Middleware_Estimate
Timelines -->
Functionality | Development | UT | AT | IT/ST | TOTAL(hours) | Start date | End Date | Status
Image Quality Check |  |  |  |  | 100
1. Write Interface MDIApplicationImageQualityInterface | 2 |  |  |  | 2 | 2015-07-24 | 2015-07-24 | Completed
a. Declare Variables and methods
2. Write MDIProfileUtilInterface | 2 |  |  |  | 2 | 2015-07-24 | 2015-07-24 | Completed
a. Declare Variables and methods
3. Write Profile Helper class | 2 |  |  |  | 2 | 2015-07-28 | 2015-07-28 | Completed
a. Implement checkQuality() | 4 | 2 | 2 | 4 | 12 | 2015-07-28 | 2015-07-28 | Dev Completed
b. Implement processImage() | 4 | 2 | 2 | 4 | 12 | 2015-07-28 | 2015-07-29 | UT Completed
4. Write ProfileUtil class | 2 |  |  |  | 2 | 2015-07-24 | 2015-07-24 | Dev Completed
a. Implement getJsonForQuality() | 4 | 2 | 2 | 8 | 16 | 2015-07-27 | 2015-07-27 | UT Completed
b. Implement getImageInBase64() | 4 | 2 | 2 | 8 | 16 | 2015-07-24 | 2015-07-24 | UT Completed
5. Write User bean and RequestResponseBean | 2 |  |  |  | 2 | 2015-07-24 | 2015-07-24 | Completed
6. Write MDIInquireImageQualityService class | 2 |  |  |  | 2 | 2015-07-28 | 2015-07-28 | Completed
a. Write getQuality() method. | 4 | 2 | 2 | 4 | 12 | 2015-07-29 | 2015-07-29 | In Progress
7. Bundle them into a jar | 2 |  |  |  | 2 | 2015-08-03 | 2015-08-03 | Open
8. Write Test classes and methods |  |  |  |  | 18 | 2015-07-29 | 2015-07-30 | In Progress
Persist New User |  |  |  |  | 61
1. Write Profile Helper class
a. Implement newUser() | 4 | 2 | 2 | 4 | 12 | 2015-08-04 | 2015-08-04 | Dev Completed
b. Implement processNewUser() | 4 | 2 | 2 | 4 | 12 | 2015-08-04 | 2015-08-04 | Dev Completed
2. Write ProfileUtil class
a. Implement getJsonForNewUser() | 4 | 2 | 2 | 8 | 12 | 2015-08-03 | 2015-08-03 | Dev Completed
3. Write MDIPersistNewUserService class | 2 |  |  |  | 2 | 2015-08-05 | 2015-08-05 | Dev Completed
a. Write getNewUser() method. | 4 | 2 | 2 | 4 | 12 | 2015-08-05 | 2015-08-05 | In Progress
4. Bundle them into a jar | 2 |  |  |  | 2 | 2015-08-06 | 2015-08-06 | Open
5. Write Test classes and methods |  |  |  |  | 9 | 2015-08-05 | 2015-08-06 | In Progress
Submit/Enroll User |  |  |  |  | 51
1. Write Interface MDIApplicationSubmitUserInterface | 2 |  |  |  | 2 | 2015-08-07 | 2015-08-07 | Open
a. Declare Variables and methods
2. Write Profile Helper class
a. Implement submitUser() | 4 | 2 | 2 | 4 | 12 | 2015-08-07 | 2015-08-07 | Open
b. Implement processInputUser() | 4 | 2 | 2 | 4 | 12 | 2015-08-07 | 2015-08-10 | Open
3. Write MDISubmitUserService class
a. Write submitUser() method. | 6 | 2 | 2 | 4 | 14 | 2015-08-10 | 2015-08-10 | Open
4. Bundle them into a jar |  |  |  |  | 2 | 2015-08-12 | 2015-08-12 | Open
5. Write Test classes and methods |  |  |  |  | 9 | 2015-08-11 | 2015-08-11 | Open
Configuration |  |  |  |  | 9 | 2015-08-13 | 2015-08-13 | Completed
AT Testing | [5 empty] | 2015-08-14 | 2015-08-19 | Open
Total |  |  |  |  | 220