## iOS_Estimate
Timelines -->
Functionality | Development(hours) | UT(hours) | Dependancy | TOTAL(hours) | Start date | End Date | Comments | Status
1. Capture the image from front or back camera of iphone.
a. Create Ui for Upload Photo in account tab. | 2 |  |  | 2 | 2015-07-27 | 2015-07-27 |  | completed
b.Capture image from front or back camera of iphone or select from the Gallery | 6 | 2 |  | 8 | 2015-07-27 | 2015-07-27 |  | completed
c.After Selecting the image crop the image to fit in square without affecting the quality | 6 | 2 |  | 8 | 2015-07-28 | 2015-07-28 |  | completed
2. Display The persisted Image on iphone.
a. Create Ui for profile Image Display in account tab. | 4 |  |  | 4 | 2015-07-29 | 2015-07-29 |  | completed
b.Call Webservice for getting url for profile pic. | 4 | 1 | Webservice from Hybris Team | 5 | 2015-08-06 |  | Started Writing client code and methods.Development Done.Getting 200 OK but not getting desired response i.e. ProfilepicURL. | In progress
c.create local db /Directory to save the profile pic | 6 | 1 |  | 7 |  |  | Waiting for the Profile Url to save in local Db. | In progress
3. Webservice implementation for Verify the quality of the image captured from iphone . |  |  | Webservice from Backend
a. Implement the request body with parameters to hit the server. | 5 | 2 |  | 7 | 2015-07-30 | 2015-08-03 | Completed Development.Facing "the requested resource does not support http method 'post'. error".Need input from biometric Team. Solved the issue with Pavan's Input on 3rd Aug | Completed
b. Manage Response and error with the alert popups. | 3 |  |  | 3 | 2015-07-31 | 2015-08-03 |  | completed
4.Webservice implementation for Persist the photo at hybris end |  |  | Webservice from Hybris Team
a. Implement the request body with parameters to hit the server. | 5 | 2 |  | 7 | 2015-08-10 |  | Need Webervice from Swarnima to proceed.Got the webservice and completed development.But not getting respose from hybris server as Enroll service is not working from Biometric. Got the Successful response on 19 Aug. | completed
b. Manage Response and error with the alert popups. | 3 |  |  | 3 | 2015-08-10 |  |  | completed
5. Webservice implementation for getting the threshold value of the image. |  |  | Webservice from Hybris Team
a. Implement the request body with parameters to hit the server. | 4 | 2 |  | 6 | 2015-08-04 | 2015-08-07 | Need Webervice from Swarnima to proceed. | completed
b. Manage Response and error with the alert popups. | 2 |  |  | 2 | 2015-08-04 | 2015-08-07 | Set up the hybris server and done initialisation to set up the code.Development Done.Not Getting response from hybris server. Got the Successful response on 7th Aug. | completed
6.Getting the details of parameters from WIFI network connected to iPhone.
a.Created ipa file for determining wifi params | 4 |  |  | 4 | 2015-07-29 | 2015-07-30 |  | completed
Total | 54 | 12 |  | 66