## iOS_Estimate
Timelines -->
Functionality | Development(hours) | UT(hours) | Dependancy | TOTAL(hours) | Start date | End Date | Status
1. Capture the image from front or back camera of iphone.
a. Create Ui for Upload Photo in account tab. | 2 |  |  | 2 | 2015-07-27 | 2015-07-27 | completed
b.Capture image from front or back camera of iphone or select from the Gallery | 6 | 2 |  | 8 | 2015-07-27 | 2015-07-27 | completed
c.After Selecting the image crop the image to fit in square without affecting the quality | 6 | 2 |  | 8 | 2015-07-28 | 2015-07-28 | completed
2. Display The persisted Image on iphone.
a. Create Ui for profile Image Display in account tab. | 4 |  |  | 4 | 2015-07-29 | 2015-07-29 | in progress
b.Call Webservice for getting url for profile pic. | 4 | 1 | Webservice from Backend | 5
c.create local db /Directory to save the profile pic | 6 | 1 |  | 7
3. Webservice implementation for Verify the quality of the image captured from iphone . |  |  | Webservice from Backend
a. Implement the request body with parameters to hit the server. | 5 | 2 |  | 7
b. Manage Response and error with the alert popups. | 3 |  |  | 3
4.Webservice implementation for Enrolling the customer. |  |  | Webservice from Backend
a. Implement the request body with parameters to hit the server. | 4 | 2 |  | 6
b. Manage Response and error with the alert popups. | 2 |  |  | 2
5.Webservice implementation for Persist the photo at hybris end |  |  | Webservice from Backend
a. Implement the request body with parameters to hit the server. | 5 | 2 |  | 7
b. Manage Response and error with the alert popups. | 3 |  |  | 3
6. Webservice implementation for getting the threshold value of the image. |  |  | Webservice from Backend
a. Implement the request body with parameters to hit the server. | 4 | 2 |  | 6
b. Manage Response and error with the alert popups. | 2 |  |  | 2
7.Getting the details of parameters from WIFI network connected to iPhone.
Total | 56 | 14 |  | 70