## Sheet1
S.No | Task description | Effort (days) | Start Date | End Date | Owner | Comments/Assumptions | Status
1 | New module creation (b2c) (name : QRScanner) | 0.5 | 2014-11-03 | 2014-11-03 | All | Download latest Hybris 5.3 and create new b2c module "QRScanner" + Ant clean all + Init + Host files entry | Completed
2 | CSR Login page | 1.5 | 2014-11-03 | 2014-11-03 | Swarnima | Just like BnC , CSR login page implementation is required here ( proper user group needs to be created) | Completed
3 | Addition of CSR Login link on the OOB Header of the storefront | 0.5 | 2014-11-03 | 2014-11-03 | Swapnil | Entry point for CSR to login. Create impex to add this link on the header component. | Completed
4 | Data modeling for new field UCOID | 0.5 | 2014-11-03 | 2014-11-03 | Prasun | Add this new field in Database + Hybris Update | Completed
5 | Data modeling for new itemtype: collectOrder (This will manage the queue for list of orders that needs to be packed and collected from counter) | 0.5 | 2014-11-04 | 2014-11-04 | Prasun | This type will have 5 attributes (1) CID, (2) OID, (3) UCOID, (4) PID, (5) Status. --> CID: Customer Id --> OID: Oder Id --> UCOID: Our new field --> PID: Product Id --> Status: Product collection status (PENDING/COMPLETED) | Completed
6 | Customize OOB Delivery method page and provide option to choose the "Pick up from next counter" option. | 1 | 2014-11-04 | 2014-11-05 | Prasun | Add new filed/drop down for "Pick up from next counter" + Hybris update + UI Changes. Also add a check that UCOID code will be generated (and will be added in queue) only when user has slected this option of delivery else its OOB. | Completed
7 | Utility class for creating UCOID(encrypted unique customer & order identifier [UCOID] on the fly based on order id, customer id, Date and Time of placing Order) | 1.5 | 2014-11-05 | 2014-11-06 | Swarnima | Complete code logic to generate and save UCOID. | Completed
8 | Interceptor class for calling and retrieving the generated UCOID from Utility class and saving the value in Order Model. | 1 | 2014-11-06 | 2014-11-07 | Swarnima |  | Completed
9 | Complete code logic to capture & save the values in "collectOrder" table (i.e. when customer who choose to collect the order places the order and when CSR agent completes the order) | 1 | 2014-11-07 | 2014-11-10 | Prasun | It is through this table the queue for order (that needs to be collected) will be managed by CSR agent, hence it needs to be updated every time with latest values. | Completed
10 | Customize Thank you page to show UCOID along with order details. | 0.5 | 2014-11-07 | 2014-11-07 | Swapnil | If the UCOID is generated than it needs to be shown on Thankyou page. Once the order is marked as complete the message should be promped to the customer to collect the order from the next counter/billing desk. On order confirmation page, UCOID is to be displayed to the customer(along with a message to not share it with anyone.) | Completed
11 | CSR Landing page to show last 5 orders ( configurable) that are pending for package & collection. | 1.5 | 2014-11-07 | 2014-11-10 | Swarnima | This will be CSR page for displaying orders placed (based on delivery Mode : Pick up from next counter) in tabular format(auto-refresh along with a refresh button) | Completed
12 | HTML integration for this CSR Landing page | 1 |  |  | Swapnil/Swarnima | Assuming HTMLs will be provided by UI team.
13 | CSR agent should have option to see all the pending orders, i.e. if more than 5 orders are pending then "Show more" link should be provided that will expand the table to show all pending order ( pagination if required) | 1.5 | 2014-11-11 | 2014-11-12 | Swapnil | Use Hybris OOB pagination feature (if required). | In Process
14 | CSR agent should have option to search the pending order details through UCOID. | 1 | 2014-11-12 | 2014-11-13 | Swapnil |  | Completed
15 | The pending order detail page should show all the details of the order & customer | 1.5 | 2014-11-11 | 2014-11-12 | Swarnima | Also on click of UCOID, This order details shall be opened along with status change drop-down (submit on value change). | Completed
16 | After marking the order as complete , the status should change in "collectOrder" table | 1 | 2014-11-12 | 2014-11-13 | Swarnima |  | Completed
17 | After the order is collected it should get removed from the pending order ( by changing the status to complete) | 1 | 2014-11-13 | 2014-11-14 | Swarnima | Order status to be updated on the order confirmation page(auto-refresh along with a refresh button)
18 | On the customer My Account create a Order Collect History page ( similar to OOB Order History page) showing the current staus of the order i.e. Pending or Complete (ready to be collected from counter). | 2 | 2014-11-11 | 2014-11-12 | Prasun |  | Completed
19 | Modify order list page related jsps Create same for mobile also | 1 | 2014-11-20 | 2014-11-20 | Swarnima | Integrate with HTML code. (index.html and css and javascripts) | Completed
20 | Modify back end functionality for order listing | 1 | 2014-11-21 | 2014-11-21 | Swarnima | 1)Remove dependency on template 2)Retrieve CSR Agent's name to show on the JSP 3)Retrieve CollectOrders Created Time Stamp in the format HH:MM AM/PM 4)Retrieve the orders statistics : 1. Queued Orders - Status as PENDING 2. Active Orders - Status as COMPLETED 3. Serviced Orders - Status as COLLECTED 4. Target - for now assuming (no. of serviced orders/total collected orders placed)*100 | Completed
21 | Modify orderDetailsPage.jsp Create same for mobile as well. | 1 | 2014-11-21 | 2014-11-21 | Swapnil | Create fragment JSPs for order details.(desktop and mobile)(JSON format)(for now basic UI as HTML code is not available for order details yet) | Completed
22 | Modify back end functionality for retrieving order and customer details through AJAX. | 0.5 | 2014-11-21 | 2014-11-24 | Swapnil | Data as per screenshots | In Progress
23 | Create functionality for retrieving orders based on Date and Time. | 2 | 2014-11-24 | 2014-11-26 | Prasun | Use createdTS attribute to compare. Integrate it with Time Search on ordersListPage.jsp
24 | Create a Sound Notification when new order is placed on CSR Dashboard | 1.5 | 2014-11-24 | 2014-11-25 | Swarnima | Add functionality for: 1. Auto Refresh the order listing(blue area only) after every 30 sec through AJAX 2. If new orders are returned through the AJAX(30 sec time interval query) , then Add more divs for the new orders below the orders list 3. Simultaneously play a notification sound 4. Simultaneously Increase the count on the bell icon | In Progress
25 | Create a sound notification when a new customer enters the store. | 1.5 | 2014-11-24 | 2014-11-25 | Swapnil | 1. Auto refresh through AJAX 2. If new customers are returned through AJAX(5 sec time interval query), add more divs for the new customers below the waiting for assistance list. 3. Simultaneously play a notification sound
26 | Change the logic of existing BNC webservice to incorporate uuid as beacon id and not as unique user id. | 1 | 2014-11-21 | 2014-11-24 | Prasun | This is done to add users in pending CSR queue based on beacon id and hence it will remove the hard coded dependency on uuid which was previously assumed to be unique user id.
27 | Change comments on the order confirmation page and Order History Page | 0.5 | 2014-11-25 | 2014-11-25 | Swarnima | Add the comments - "Kindly collect your order from Aisle 10"