## Sheet1
Functionality | Development | UT | AT | IT/ST | TOTAL(hours) | Developer | Start date | End Date | Status
1. Create a new extension named qrcode using yempty as template | 2 |  |  |  |  | Jayasree | 2015-07-24 | 2015-07-24 | Completed
2. Separate the items and related code from qrcodeaddon. And add it in the extension created above. |  |  |  |  | 19
a. Move item types | 3
b. Move data objects | 2
c. Test and move other related independent classes | 4 | 2 | 2 | 4
d. Modify dependencies on classes inside qrcodeaddon | 2
3. Create a new addon "facerecognitionaddon". Install the addon on bncwebservices and storefront | 4 |  |  |  | 4 | Jayasree | 2015-07-24 | 2015-07-24 | Completed
4. Add itemtypes | 4 |  |  |  | 4 | Jayasree | 2015-07-24 | 2015-07-24 | Completed
5. Add data objects through beans.xml | 2 |  |  |  | 2 | Jayasree | 2015-07-27 | 2015-07-27 | Completed
6. Create ImageQualityPopulator with spring configuration | 4 |  |  |  | 4 | Jayasree | 2015-07-27 | 2015-07-27 | Completed
7. Add a new CMS page for uploading profile picture with same template as account |  |  |  |  | 16
a. Create controller with GET method(MDIYImageQualityCheckController) | 4 | 2 | 2 | 2 |  | Jayasree | 2015-07-27 | 2015-07-28 | In progress
b. Write the JSP to be rendered | 2
c. Create the method saveCustomerDetails which is triggered on load of profile pic | 4
8. Create MDIYCustomerDataFacade | 1 | 2 | 2 | 4 | 22
9. Create MDIYCustomerDataFacadeImpl
a.Implement saveCustomerImage() | 4
b.Implement saveCustomerData() | 2
10. Create MDIYCustomerDataService | 1
11. Create MDIYSaveCustomerDataServiceImpl
a. Implement saveCustomerData() | 6
12. Create a new webservice controller MDIYImageUploadByMobileController |  | 2 | 2 | 2 | 12
a. Create saveCustomerDetails() | 4
b. Create getCustomerDataFromJsonString() | 2
c. Create populateCustomerData() | 2
13. Add method persistNewUser to existing controller MDIYImageQualityCheckController | 4 |  |  |  | 17
8. Create MDIYSaveBiometricDataFacade | 1 | 2 | 2 | 2
9. Create MDIYSaveBiometricDataFacadeImpl
a. Declare variables and methods
b.Implement saveBiometricData() | 2
10. Create MDIYCustomerDataService | 1
11. Create MDIYSaveCustomerDataServiceImpl
a.implement saveBiometricData() | 3
11. Create cronjob MDIYPersistUserCronJob | 6 | 2 |  | 2 | 10
13. Create Controller MDIYSubmitUserController |  | 2 | 2 | 4 | 31
a. Declare variables and methods | 3
8. Create MDIYSubmitUserFacade | 1
9. Create MDIYSubmitUserFacadeImpl
a.Implement addUserToQueue() | 4
10. Create MDIYSubmitUserService | 1
11. Create MDYSubmitUserServiceImpl
a.Implement addUserToQueue() | 3
10. Create MDIYSubmitUserDao | 1
11. Create MDYSubmitUserDaoImpl
a.Implement doesCustomerExist() | 3
12. Create MDIYCSRCustomerPopulator | 3
13. Create MDIYImagePopulator | 4
Configuration |  |  |  |  | 9
Total |  |  |  |  | 150