## Middleware_Estimate
Timelines -->
Functionality | Development | UT | AT | IT/ST | TOTAL(hours) | Start date | End Date | Status
Image Quality Check |  |  |  |  | 100
1. Write Interface MDIApplicationImageQualityInterface | 2 |  |  |  | 2 | 2015-07-24 | 2015-07-24 | Completed
a. Declare Variables and methods
2. Write MDIProfileUtilInterface | 2 |  |  |  | 2 | 2015-07-24 | 2015-07-24 | Completed
a. Declare Variables and methods
3. Write Profile Helper class | 2 |  |  |  | 2 | 2015-07-28 | 2015-07-28 | in progress
a. Implement checkQuality() | 4 | 2 | 2 | 4 | 12 | 2015-07-28 | 2015-07-28 | in progress
b. Implement processImage() | 4 | 2 | 2 | 4 | 12 | 2015-07-28 | 2015-07-28 | in progress
4. Write ProfileUtil class | 2 |  |  |  | 2
a. Implement getJsonForQuality() | 4 | 2 | 2 | 8 | 16 | 2015-07-27 | 2015-07-27 | Completed
b. Implement getImageInBase64() | 4 | 2 | 2 | 8 | 16 | 2015-07-24 | 2015-07-24 | Completed
5. Write User bean and RequestResponseBean | 2 |  |  |  | 2
6. Write MDIInquireImageQualityService class | 2 |  |  |  | 2
a. Write getQuality() method. | 4 | 2 | 2 | 4 | 12
7. Bundle them into a jar | 2 |  |  |  | 2
8. Write Test classes and methods |  |  |  |  | 18
Persist New User |  |  |  |  | 61
1. Write Profile Helper class
a. Implement newUser() | 4 | 2 | 2 | 4 | 12
b. Implement processNewUser() | 4 | 2 | 2 | 4 | 12
2. Write ProfileUtil class
a. Implement getJsonForNewUser() | 4 | 2 | 2 | 8 | 12
3. Write MDIPersistNewUserService class | 2 |  |  |  | 2
a. Write getQuality() method. | 4 | 2 | 2 | 4 | 12
4. Bundle them into a jar | 2 |  |  |  | 2
5. Write Test classes and methods |  |  |  |  | 9
Submit/Enroll User |  |  |  |  | 51
1. Write Interface MDIApplicationSubmitUserInterface | 2 |  |  |  | 2
a. Declare Variables and methods
2. Write Profile Helper class
a. Implement submitUser() | 4 | 2 | 2 | 4 | 12
b. Implement processInputUser() | 4 | 2 | 2 | 4 | 12
3. Write MDISubmitUserService class
a. Write submitUser() method. | 6 | 2 | 2 | 4 | 14
4. Bundle them into a jar |  |  |  |  | 2
5. Write Test classes and methods |  |  |  |  | 9
Configuration |  |  |  |  | 9
Total |  |  |  |  | 220