## Sheet1
S.No | Task description | Effort (days) | Effort (hours) | Start Date | End Date | Owner | Comments/Assumptions | Status
0 | Create Addon named "healthpromotionsaddon" | 0 | 0 | 2015-01-08 | 2015-01-08 | Swarnima / Swapnil | Create a separate functionality altogether. Including bncwebservices | Completed
1 | Impex to create new category "Health Products" in existing electronics store catalog. | 0.5 | 4 | 2015-01-08 | 2015-01-08 | Swapnil | This category will hold all the new health related products (Note: Since all these are elecronic products we will keep it under electronics catalog). | Completed
2 | Add all the required permissions to this new category so that its accessible by relevant user groups. | 0.5 | 4 | 2015-01-08 | 2015-01-08 | Swapnil | After above steps & hybris update verify that new products have been added in database and are accessible on PDP pages etc. | Completed
3 | Impex to import health product data (and Image) in database. Assumption: Image is provided by UI team. | 3 | 24 | 2015-01-09 | 2015-01-22 | Swarnima / Swapnil | Create following impex to import the new health related electronics products in database. (1) product.impex (2) products-media.impex (3) products_en.impex (4) products-prices.impex (5) products-relations.impex (6) products-stocklevels.impex (7) warehouses.impex | Completed
4 | Create a new data model for managing health related customer data. | 0.5 | 4 | 2015-01-08 | 2015-01-08 | Swarnima | This new data model "CustomerHealthData" should have following fields: (1) Heart beat rate (2) Blood Pressure (3) Miles run (4) Calories burned (5) Time taken (6) Age (7) CustomerId | Completed
5 | Create web service to get all the customer exercise data (heartbeat, blood pressure, miles, calories, time, age) through url of the web service. | 1.5 | 12 | 2015-01-08 | 2015-01-09 | Swarnima | The web service will be accessible through following URL. http://localhost:9001/bncwebservices/v1/electronics/CustomerHealthData The values shall be passed as a JSON object as follows: {‘HealthData’: [ {‘type’: ‘customerId’, ‘Value’ : ‘123’}, {‘type’: ‘heartbeatrate’, ‘Value’ : ‘72’}, {‘type’: ‘bloodPressure’, ‘Value’ : ‘80’} ] } and so on.. The significance of values are as follows: 60 - Heart beat per minute 100 - blood pressure (mmHg) 1.5 - Miles run 150 - Calories burned 30 - minutes 29 - Age | Completed
6 | Implementation of backend logic to save all the data retrieved from web service in database. | 1 | 8 | 2015-01-19 | 2015-01-19 | Swarnima | This will involve façade, service, dao layer etc. | Completed
7 | Create a new item type "beacon" having following attributes: 1.) Id 2.) MajorId 3.) MinorId 4.) Welcome Message | 0.5 | 4 | 2015-01-21 | 2015-01-21 | Swarnima | This will hold data for all beacon including its major & minor Id. | Completed
8 | Create a N-N relation between "beacon" and "AbstractPromotions" | 0.5 | 4 | 2015-01-21 | 2015-01-21 | Swarnima | This relation is required because multiple promotions can be associated with one beacon and at same time one promotion can be associated with multiple beacon also, hence N-N relation. | Completed
9 | Create few promotions and beacon instances through HMC and associate the promotions with beacon instances so created. Note: Create Impex for the same. | 0.5 | 4 | 2015-01-22 | 2015-01-22 | Swapnil | This is to be done through HMC. The idea is to have multiple instances of promotions and beacon present in the database so that the promotional webservice could retrieve the same. | Completed
10 | Create promotional web service specific to beacon id. | 2.5 | 20 | 2015-01-22 | 2015-01-27 | Swarnima | This URL of the web service will be like : http://localhost:9001/bncwebservices/v1/electronics/BeaconPromotions/eda4b92b-07ab-4ca4-8ecd-43d53123bd98/000001/000002 Here "eda4b92b-07ab-4ca4-8ecd-43d53123bd98" is beacon id, "000001" is major Id and "000002" is minor Id. Note: This webservice will return the welcome message and all the promotions associated with this beacon id. Example : Welcome Message :=> Welcome to our Store! 30 % off on Digital cameras for today only. Promotions :=> 1.) Buy one get one free. 2.) Get SD card free with Samsung mobiles. | Completed
11 | Create few promotions and assign a relevant user group (having your target customer) to it. Note: Create Impex for the same. | 1 | 8 | 2015-01-22 | 2015-01-23 | Swapnil | This is customer specific promotion so beaconId need not be present here. The idea is to group the target customers based on there health data and then offer promotions to them. Example: All the customers who run more than 1 Mile per day can be offered discount on sports shoes. | Completed
12 | Create one more promotional web service specific to the customer. This will return all the promotions that are applicable for the user group of this user. | 2.5 | 20 | 2015-01-23 | 2015-01-28 | Swapnil | This URL of the web service will be like : http://localhost:9001/bncwebservices/v1/electronics/CustomerHealthPromotions/neeraj.a.shah@accenture.com Here the only parameter "neeraj.a.shah@accenture" is the unique email id of the user. Note: This webservice will return all the promotions associated with the mention user. | Completed
13 | Create a cron job to send mails to the customers who are eligible for promotions. | 2.5 | 20 | 2015-01-27 | 2015-01-29 | Swarnima | This will involve new entry in item.xml, spring.xml, extension of job performable class and implementation of perform method() having logic to retrieve all the customers that are eligible for promotions. Note: It will internally use above mention web service to check for the promotions based on customer Id. | Completed
14 | Triggering emails to the customer. | 2 | 16 | 2015-01-30 | 2015-02-02 | Swarnima | This will involve setting up SMTP server , setting up mail templates and then triggering mail to the customer with the relevant promotion information retrieved from the above web service. | Completed
15 | Extend the Product data model to add "beaconId" and "location" attributes. | 0.5 | 4 | 2015-01-29 | 2015-01-29 | Swapnil | This is done to associate products with beacon id and to store location of the products . (location will be seprated by ‘¦’ character e.g. Aisle 2B¦Wing 4¦Floor 3) | Completed
16 | Create Impex to insert beaconId and location data in the product table. | 0.5 | 4 | 2015-01-29 | 2015-01-29 | Swapnil | This data will be used by relevant web services. | Completed
17 | Create web service to retrieve all the product details (location etc) depending on the beacon id. | 2 | 16 | 2015-01-30 | 2015-02-02 | Swapnil | This URL of the web service will be like : http://localhost:9001/bncwebservices/v1/electronics/ProductLocationDetails/eda4b92b-07ab-4ca4-8ecd-43d53123bd98/ Here the only parameter "eda4b92b-07ab-4ca4-8ecd-43d53123bd98" is beacon id. Note: This webservice will return all the products that are associate (i.e. at the same location) with the provided beacon id. | Completed
18 | Customize OOB product based web service to return beacon Id and location details of the product along with other OOB product details. | 1.5 | 12 | 2015-02-03 | 2015-02-04 | Swapnil | This will require customization of OOB product webservice (http://localhost:9001/bncwebservices/v1/electronics/products/553637?options=DESCRIPTION) to return product location & beacon Id associate with that product. | Completed

## Defects
S.No | Defect description | Effort (days) | Start Date | End Date | Owner | Status | Comments
1 | OOB products and category pages not opening - 404 not found error |  |  |  | Swarnima | Closed
2 | Send UCOID along with the other order details through in existing webservice |  |  |  | Swarnima | Closed
3 | Change the return type of Beacon webservice to JSON |  |  |  | Swarnima | Closed
4 | Customer Health Data webservice not recognising the customer. Showing customer not found. |  |  |  | Swarnima | Closed
5 | Products are not adding to recently viewed list when viewed from the mobile application |  |  |  | Swapnil | Closed
6 | Existing UI fixes:
7 | Remove dependency on bncstorefront for dummy images for customers showing on csr dashboard |  |  |  | Swarnima | Closed
8 | Image size fix for left navigation |  |  |  | Swarnima | Closed
9 | Change the bell shound for both Customers and Orders Dashboard |  |  |  | Swapnil | Closed
10 | Carousel functionality for wishlist, recently viewed and recommended products not working. |  |  |  | Swarnima | Closed
11 | Align customer details properly on personal page on orders dashboard |  |  |  | Swarnima | Closed
12 | % sign not showing in target |  |  |  | Swapnil | Open
13 | Pie charts not working for dynamic values. Charts are showing only when we hardcode the values in the JSP. |  |  |  | Senthil | Open | As a temporary solution, we have implemented the Old UI charts for the demo. But we need to look into this.
14 | The UI is not responsive. |  |  |  | Senthil | Open | Distorted on Ipad
15 | The Header left navigation remains open on ipad |  |  |  | Senthil | Open
16 | The right hand hovering menu for signing out a CSR Agent is not opening on ipad |  |  |  | Senthil | Open
17 | Only 1 customer is shown on the left navigation even when there are more than 1 customers. The other customer appears only when the first one has been removed from the queue. |  |  |  | Swarnima | Closed
18 | Move the assist/Serviced/No Thanks button up right next to the customer's image and below the customer's name |  |  |  | Swapnil | Closed
19 | The whole page should not refresh, only the required divs should refresh, a. the left nav section for customers/orders b. the charts c. if required the right section also. |  |  |  | Swarnima | Closed
20 | Change the beacon item type and make the beaconid, majorId and minorId unique attributes. Also test with the impexes to see whether beacon with same beaconId and different major and minor Ids are being saved to the database. |  |  |  | Swapnil | Closed
| The accordion on order history tab overlaps the order details with other accordion tabs |  |  |  | Swapnil | Open

## Addtnl Tasks
S.No | Defect description | Effort (days) | Start Date | End Date | Owner | Explanation | Status
1 | Create a new webservice for detecting a beacon and performing 2 tasks - showing promotions and welcome messages, and adding customer to the waiting queue Merge the 2 existing webservices for beacon detection in 1 |  |  |  | Swarnima |  | Completed
2 | Integration of new UI |  |  |  | Swarnima/Swapnil |  | Currently On Hold
3 | Change the return type of Customer Health Data webservice to JSON |  |  |  | Swarnima |  | Completed
4 | Create a new webservice for retrieving all the beacon ids and their major and minor ids |  |  |  | Swapnil |  | Completed
5 | Create a new webservice for retrieving all the customer's collect orders |  |  |  | Swarnima |  | Completed
6 | Add the additional Customer Health Data attributes and modify related code for the saving the health data for the customer |  |  |  | Swapnil |  | Completed
7 | Move the default beacon and their major and minor ids to properties file(the beacon which adds the customer to the waiting queue) for easy change in future |  |  |  | Swarnima |  | Completed
8 | Create webservice for sending all wishlist products for the customer. | 1.5 | 2015-03-02 | 2015-03-03 | Swarnima | This webservice will receive the JSON object as {"uid":"sdsf@cccccbc.com"} And it will send the ProductDataList The URL of the webservice will be: http://localhost:9001/bncwebservices/v1/electronics/wishlist/get | Completed
9 | Create webservice for adding a product to the wishlist for a customer | 1 | 2015-03-03 | 2015-03-04 | Swarnima | This webservice will receive the JSON object as {"uid":"sdsf@cccccbc.com","productId":"4567"} And it will send the ProductDataList The URL of the webservice will be: http://localhost:9001/bncwebservices/v1/electronics/wishlist/add | Completed
10 | Create webservice for removing a product from the wishlist for a customer | 1 | 2015-03-03 | 2015-03-04 | Swapnil | This webservice will receive the JSON object as {"uid":"sdsf@cccccbc.com","productId":"4567"} And it will send the ProductDataList The URL of the webservice will be: http://localhost:9001/bncwebservices/v1/electronics/wishlist/remove | Completed
11 | Modify the beacon promotions webservices, to send out the promotions based on the customer's and beacon's promotions groups | 1 | 2015-03-04 | 2015-03-05 | Swarnima | Modify the beacon promotions webservices, to send out the promotions based on the customer's and beacon's promotions groups(with no duplications) | Completed
12