## iOS_Estimate
Timelines -->
Functionality | Development(hours) | UT(hours) | Dependancy | TOTAL(hours) | Start date | End Date | Comments | Status
1. Capture the image from front or back camera of iphone.
a. Create Ui for Upload Photo in account tab. | 2 |  |  | 2 | 2015-07-27 | 2015-07-27 |  | completed
b.Capture image from front or back camera of iphone or select from the Gallery | 6 | 2 |  | 8 | 2015-07-27 | 2015-07-27 |  | completed
c.After Selecting the image crop the image to fit in square without affecting the quality | 6 | 2 |  | 8 | 2015-07-28 | 2015-07-28 |  | completed
2. Display The persisted Image on iphone.
a. Create Ui for profile Image Display in account tab. | 4 |  |  | 4 | 2015-07-29 | 2015-07-29 |  | completed
b.Call Webservice for getting url for profile pic. | 4 | 1 | Webservice from Hybris Team | 5
c.create local db /Directory to save the profile pic | 6 | 1 |  | 7
3. Webservice implementation for Verify the quality of the image captured from iphone . |  |  | Webservice from Backend
a. Implement the request body with parameters to hit the server. | 5 | 2 |  | 7 | 2015-07-30 | 2015-08-03 | Completed Development.Facing "the requested resource does not support http method 'post'. error".Need input from biometric Team. Solved the issue with Pavan's Input on 3rd Aug | Completed
b. Manage Response and error with the alert popups. | 3 |  |  | 3 | 2015-07-31 | 2015-08-03 |  | completed
4.Webservice implementation for Persist the photo at hybris end |  |  | Webservice from Hybris Team
a. Implement the request body with parameters to hit the server. | 5 | 2 |  | 7
b. Manage Response and error with the alert popups. | 3 |  |  | 3
5. Webservice implementation for getting the threshold value of the image. |  |  | Webservice from Hybris Team
a. Implement the request body with parameters to hit the server. | 4 | 2 |  | 6 | 2015-08-04 |  | Need Webervice from Swarnima to proceed. | In progress
b. Manage Response and error with the alert popups. | 2 |  |  | 2 | 2015-08-04 |  |  | In progress
6.Getting the details of parameters from WIFI network connected to iPhone.
a.Created ipa file for determining wifi params | 4 |  |  | 4 | 2015-07-29 | 2015-07-30 |  | completed
Total | 54 | 12 |  | 66