## Sheet1
S.No | Task description | Effort (days) | Effort (hours) | Start Date | End Date | Owner | Comments/Assumptions | Status
0 | Create Addon named "healthpromotionsaddon" | 0 | 0 | 2015-01-08 | 2015-01-08 | Swarnima / Swapnil | Create a separate functionality altogether. Including bncwebservices | Completed
1 | Impex to create new category "Health Products" in existing electronics store catalog. | 0.5 | 4 | 2015-01-08 | 2015-01-08 | Swapnil | This category will hold all the new health related products (Note: Since all these are elecronic products we will keep it under electronics catalog). | Completed
2 | Add all the required permissions to this new category so that its accessible by relevant user groups. | 0.5 | 4 | 2015-01-08 | 2015-01-08 | Swapnil | After above steps & hybris update verify that new products have been added in database and are accessible on PDP pages etc. | Completed
3 | Impex to import health product data (and Image) in database. Assumption: Image is provided by UI team. | 3 | 24 | 2015-01-09 | 2015-01-22 | Swarnima / Swapnil | Create following impex to import the new health related electronics products in database. (1) product.impex (2) products-media.impex (3) products_en.impex (4) products-prices.impex (5) products-relations.impex (6) products-stocklevels.impex (7) warehouses.impex | Completed
4 | Create a new data model for managing health related customer data. Note: It should extend User Data model. | 0.5 | 4 | 2015-01-08 | 2015-01-08 | Swarnima | This new data model "CustomerHealthData" should have following fields: (1) Heart beat rate (2) Blood Pressure (3) Miles run (4) Calories burned (5) Time taken (6) Age | Completed
5 | Create web service to get all the customer exercise data (heartbeat, blood pressure, miles, calories, time, age) through url of the web service. | 1.5 | 12 | 2015-01-08 | 2015-01-09 | Swarnima | The web service will be accessible through following URL. http://localhost:9001/bncwebservices/v1/electronics/CustomerHealthData/60/100/1.5/150/30/29 The significance of values are as follows: 60 - Heart beat per minute 100 - blood pressure (mmHg) 1.5 - Miles run 150 - Calories burned 30 - minutes 29 - Age | Completed
6 | Implementation of backend logic to save all the data retrieved from web service in database. | 1 | 8 | 2015-01-19 | 2015-01-19 | Swarnima | This will involve façade, service, dao layer etc. | Completed
7 | Create a new item type "beacon" having following attributes: 1.) Id 2.) MajorId 3.) MinorId 4.) Welcome Message | 0.5 | 4 | 2015-01-21 | 2015-01-21 | Swarnima | This will hold data for all beacon including its major & minor Id. | Completed
8 | Create a N-N relation between "beacon" and "AbstractPromotions" | 0.5 | 4 | 2015-01-21 | 2015-01-21 | Swarnima | This relation is required because multiple promotions can be associated with one beacon and at same time one promotion can be associated with multiple beacon also, hence N-N relation. | Completed
9 | Create few promotions and beacon instances through HMC and associate the promotions with beacon instances so created. Note: Create Impex for the same. | 0.5 | 4 | 2015-01-22 | 2015-01-22 | Swapnil | This is to be done through HMC. The idea is to have multiple instances of promotions and beacon present in the database so that the promotional webservice could retrieve the same. | Completed
10 | Create promotional web service specific to beacon id. | 2.5 | 20 | 2015-01-22 | 2015-01-27 | Swarnima | This URL of the web service will be like : http://localhost:9001/bncwebservices/v1/electronics/BeaconPromotions/eda4b92b-07ab-4ca4-8ecd-43d53123bd98/000001/000002 Here "eda4b92b-07ab-4ca4-8ecd-43d53123bd98" is beacon id, "000001" is major Id and "000002" is minor Id. Note: This webservice will return the welcome message and all the promotions associated with this beacon id. Example : Welcome Message :=> Welcome to our Store! 30 % off on Digital cameras for today only. Promotions :=> 1.) Buy one get one free. 2.) Get SD card free with Samsung mobiles. | Completed
11 | Create few promotions and assign a relevant user group (having your target customer) to it. Note: Create Impex for the same. | 1 | 8 | 2015-01-22 | 2015-01-23 | Swapnil | This is customer specific promotion so beaconId need not be present here. The idea is to group the target customers based on there health data and then offer promotions to them. Example: All the customers who run more than 1 Mile per day can be offered discount on sports shoes. | Completed
12 | Create one more promotional web service specific to the customer. This will return all the promotions that are applicable for the user group of this user. | 2.5 | 20 | 2015-01-23 | 2015-01-28 | Swapnil | This URL of the web service will be like : http://localhost:9001/bncwebservices/v1/electronics/CustomerHealthPromotions/neeraj.a.shah@accenture.com Here the only parameter "neeraj.a.shah@accenture" is the unique email id of the user. Note: This webservice will return all the promotions associated with the mention user. | Completed
13 | Create a cron job to send mails to the customers who are eligible for promotions. | 2.5 | 20 | 2015-01-27 | 2015-01-29 | Swarnima | This will involve new entry in item.xml, spring.xml, extension of job performable class and implementation of perform method() having logic to retrieve all the customers that are eligible for promotions. Note: It will internally use above mention web service to check for the promotions based on customer Id. | Completed
14 | Triggering emails to the customer. | 2 | 16 | 2015-01-30 | 2015-02-02 | Swarnima | This will involve setting up SMTP server , setting up mail templates and then triggering mail to the customer with the relevant promotion information retrieved from the above web service. | Completed
15 | Extend the Product data model to add "beaconId" and "location" attributes. | 0.5 | 4 | 2015-01-29 | 2015-01-29 | Swapnil | This is done to associate products with beacon id and to store location of the products . (location will be seprated by ‘¦’ character e.g. Aisle 2B¦Wing 4¦Floor 3) | Completed
16 | Create Impex to insert beaconId and location data in the product table. | 0.5 | 4 | 2015-01-29 | 2015-01-29 | Swapnil | This data will be used by relevant web services. | Completed
17 | Create web service to retrieve all the product details (location etc) depending on the beacon id. | 2 | 16 | 2015-01-30 | 2015-02-02 | Swapnil | This URL of the web service will be like : http://localhost:9001/bncwebservices/v1/electronics/ProductsLocationDetails/eda4b92b-07ab-4ca4-8ecd-43d53123bd98/ Here the only parameter "eda4b92b-07ab-4ca4-8ecd-43d53123bd98" is beacon id. Note: This webservice will return all the products that are associate (i.e. at the same location) with the provided beacon id. | Completed
18 | Customize OOB product based web service to return beacon Id and location details of the product along with other OOB product details. | 1.5 | 12 | 2015-02-03 | 2015-02-04 | Swapnil | This will require customization of OOB product webservice (http://localhost:9001/bncwebservice/v1/electronics/products/553637?options=DESCRIPTION) to return product location & beacon Id associate with that product. | Completed