## UI_Estimate
Timelines -->
Functionality | Development | UT | AT | IT/ST | TOTAL(hours) | Start date | End Date | Status
1. CSR Dashboard
a. VD for CSR Dashboard page | 9 |  |  |  | 9
b. HTML for CSR Dashboard page(with all functionality) | 45 |  |  |  | 45
c. HTML rework | 30 |  |  |  | 30
d. Added Geolocation Tab | 12 |  |  |  | 12
e. Fix Responsive layout issues | 25 |  |  |  | 25
f. Fix chart Issue | 14 |  |  |  | 14
g. Separate HTML File conversion | 12 |  |  |  | 12
h. UI Screen for Non Register Customers | 30 |  |  |  | 30 | 2015-07-27 | 2015-07-30 | Done
i. CSR Dashboard design for Ipad mini | 20 |  |  |  | 20 | 2015-08-13 |  | In progress
2. Store Dashboard
a. Wireframe for Dashboard page | 18 |  |  |  | 18
b. Wireframe rework | 4 |  |  |  | 4
d. VD for Store Dashboard page | 9 |  |  |  | 9
e. HTML for Store Dashboard page | 27 |  |  |  | 27
f. HTML for Store Dashboard page (With Physical profile widget) | 18 |  |  |  | 18
g. HTML for Store Dashboard page (With Modal Window) | 45 |  |  |  | 45
h. Store Dashboard design for Ipad mini | 20 |  |  |  | 20 | 2015-08-13 |  | In progress
Browse button functionality | 9 |  |  |  | 9
Navigation Tab Functionality | 6 |  |  |  | 6
3. Map Functionality in Store dashboard
a. Map need to revamp like google map (zoom in and zoom out) | 45 |  |  |  | 45 | 2015-07-20 | 2015-07-24 | Done
b. If implement the Google Map API, some existing functionalities need to fix | 25 |  |  |  | 25 | 2015-07-24 | 2015-08-10 | Done
Total |  |  |  |  | 383