## Sheet1
S.No | Task description | Effort (days) | Start Date | End Date | Owner | Comments/Assumptions
1 | New module creation (b2c) (name : QRScanner) | 0.5 | 2014-11-03 | 2014-11-03 | All | Download latest Hybris 5.3 and create new b2c module "QRScanner" + Ant clean all + Init + Host files entry
2 | Data modeling for new field UCOID | 0.5 | 2014-11-03 | 2014-11-03 | Prasun | Add this new field in Database + Hybris Update
3 | Utility class for creating UCOID(encrypted unique customer & order identifier [UCOID] on the fly based on order id, customer id, Date and Time of placing Order) | 1.5 | 2014-11-04 | 2014-11-05 | Prasun | Complete code logic to generate and save UCOID.
4 | Interceptor class for calling and retrieving the generated UCOID from Utility class and saving the value in Order Model. | 0.5 | 2014-11-05 | 2014-11-05 | Prasun
5 | Data modeling for new itemtype: collectOrder (This will manage the queue for list of orders that needs to be packed and collected from counter) | 0.5 | 2014-11-06 | 2014-11-06 | Prasun | This type will have 5 attributes (1) CID, (2) OID, (3) UCOID, (4) PID, (5) Status. --> CID: Customer Id --> OID: Oder Id --> UCOID: Our new field --> PID: Product Id --> Status: Product collection status (PENDING/COMPLETED)
6 | Complete code logic to capture & save the values in "collectOrder" table (i.e. when customer who choose to collect the order places the order and when CSR agent completes the order) | 1 | 2014-11-06 | 2014-11-07 | Prasun | It is through this table the queue for order (that needs to be collected) will be managed by CSR agent, hence it needs to be updated every time with latest values.
7 | Customize OOB Delivery method page and provide option to choose the "Pick up from next counter" option. | 1 | 2014-11-07 | 2014-11-10 | Prasun | Add new filed/drop down for "Pick up from next counter" + Hybris update + UI Changes. Also add a check that UCOID code will be generated (and will be added in queue) only when user has slected this option of delivery else its OOB.
8 | Customize Thank you page to show UCOID along with order details. | 0.5 | 2014-11-10 | 2014-11-10 | Prasun | If the UCOID is generated than it needs to be shown on Thankyou page.
9 | CSR Login page | 1.5 | 2014-11-03 | 2014-11-04 | Swarnima | Just like BnC , CSR login page implementation is required here ( proper user group needs to be created)
10 | Addition of CSR Login link on the OOB Header of the storefront | 0.5 | 2014-11-04 | 2014-11-04 | Swapnil | Entry point for CSR to login. Create impex to add this link on the header component.
11 | CSR Landing page to show last 5 orders ( configurable) that are pending for package & collection. | 1.5 | 2014-11-10 | 2014-11-11 | Swarnima | This will be CSR page for displaying orders placed (based on delivery Mode : Pick up from next counter) in tabular format(auto-refresh along with a refresh button)
12 | HTML integration for this CSR Landing page | 1 |  |  | Swapnil/Swarnima | Assuming HTMLs will be provided by UI team.
13 | CSR agent should have option to see all the pending orders, i.e. if more than 5 orders are pending then "Show more" link should be provided that will expand the table to show all pending order ( pagination if required) | 1.5 | 2014-11-11 | 2014-11-12 | Swapnil | Use Hybris OOB pagination feature (if required).
14 | CSR agent should have option to search the pending order details through UCOID. | 1 | 2014-11-11 | 2014-11-12 | Swapnil
15 | The pending order detail page should show all the details of the order & customer | 1.5 | 2014-11-12 | 2014-11-13 | Swarnima | Also on click of UCOID, This order details shall be opened along with status change drop-down (submit on value change).
16 | After marking the order as complete , the status should change in "collectOrder" table | 0.5 | 2014-11-14 | 2014-11-14 | Swarnima
17 | Once the order is marked as complete the message should be promped to the customer to collect the order from the next counter/billing desk. | 0.5 | 2014-11-14 | 2014-11-14 | Swapnil | On order confirmation page, UCOID is to be displayed to the customer(along with a message to not share it with anyone.)
18 | After the order is collected it should get removed from the pending order list as well as from the "collectOrder" table. | 0.5 | 2014-11-17 | 2014-11-17 | Swarnima | Order status to be updated on the order confirmation page(auto-refresh along with a refresh button)