## Sheet1
S.No | Task description | Effort (days) | Effort (hours) | Start Date | End Date | Owner | Comments/Assumptions | Status
1 | Impex to create new category "Health Products" in existing electronics store catalog. | 0.5 | 4 |  |  |  | This category will hold all the new health related products (Note: Since all these are elecronic products we will keep it under electronics catalog).
2 | Impex to import health product data (and Image) in database. Assumption: Image is provided by UI team. | 3 | 24 |  |  |  | Create following impex to import the new health related electronics products in database. (1) product.impex (2) products-media.impex (3) products_en.impex (4) products-prices.impex (5) products-relations.impex (6) products-stocklevels.impex (7) warehouses.impex
3 | Add all the required permissions to this new category so that its accessible by relevant user groups. | 0.5 | 4 |  |  |  | After above steps & hybris update verify that new products have been added in database and are accessible on PDP pages etc.
4 | Create a new data model for managing health related customer data. Note: It should extend User Data model. | 0.5 | 4 |  |  |  | This new data model "CustomerHealthData" should have following fields: (1) Heart beat rate (2) Blood Pressure (3) Miles run (4) Calories burned (5) Time taken (6) Age
5 | Create web service to get all the customer exercise data (heartbeat, blood pressure, miles, calories, time, age) through url of the web service. | 1.5 | 12 |  |  |  | The web service will be accessible through following URL. http://localhost:9001/bncwebservices/v1/electronics/CustomerHealthData/60/100/1.5/150/30/29 The significance of values are as follows: 60 - Heart beat per minute 100 - blood pressure (mmHg) 1.5 - Miles run 150 - Calories burned 30 - minutes 29 - Age
6 | Implementation of backend logic to save all the data retrieved from web service in database. | 1 | 8 |  |  |  | This will involve façade, service, dao layer etc.
7 | Extend "AbstractPromotion" and add new attribute "beaconId" in it. | 0.5 | 4 |  |  |  | This is done to associate beacon id with promotions.
8 | Create few promotions and provide beacon Id in the beaconId attribute Note: Create Impex for the same. | 0.5 | 4 |  |  |  | This is to be done through HMC. The idea is to have promotions specific to beacon id present in database so that the relevant webservice could retrieve it.
9 | Create promotional web service specific to beacon id. | 2 | 16 |  |  |  | This URL of the web service will be like : http://localhost:9001/bncwebservices/v1/electronics/BeaconPromotions/eda4b92b-07ab-4ca4-8ecd-43d53123bd98/ Here the only parameter "eda4b92b-07ab-4ca4-8ecd-43d53123bd98" is beacon id. Note: This webservice will return all the promotions associated with this beacon id. Example : Welcome to our Store! 30 % off on Digital cameras for today only.
10 | Create few promotions and assign a relevant user group (having your target customer) to it. Note: Create Impex for the same. | 1 | 8 |  |  |  | This is customer specific promotion so beaconId need not be present here. The idea is to group the target customers based on there health data and then offer promotions to them. Example: All the customers who run more than 1 Mile per day can be offered discount on sports shoes.
11 | Create one more promotional web service specific to the customer. This will return all the promotions that are applicable for the user group of this user. | 2.5 | 20 |  |  |  | This URL of the web service will be like : http://localhost:9001/bncwebservices/v1/electronics/CustomerHealthPromotions/neeraj.a.shah@accenture.com Here the only parameter "neeraj.a.shah@accenture" is the unique email id of the user. Note: This webservice will return all the promotions associated with the mention user.
12 | Create a cron job to send mails to the customers who are eligible for promotions. | 2.5 | 20 |  |  |  | This will involve new entry in item.xml, spring.xml, extension of job performable class and implementation of perform method() having logic to retrieve all the customers that are eligible for promotions. Note: It will internally use above mention web service to check for the promotions based on customer Id.
13 | Triggering emails to the customer. | 2 | 16 |  |  |  | This will involve setting up SMTP server , setting up mail templates and then triggering mail to the customer with the relevant promotion information retrieved from the above web service.
14 | Extend the Product data model to add "beaconId" and "location" attributes. | 0.5 | 4 |  |  |  | This is done to associate products with beacon id and to store location of the products . (location will be seprated by ‘¦’ character e.g. Aisle 2B¦Wing 4¦Floor 3)
15 | Create Impex to insert beaconId and location data in the product table. | 0.5 | 4 |  |  |  | This data will be used by relevant web services.
16 | Create web service to retrieve all the product details (location etc) depending on the beacon id. | 2 | 16 |  |  |  | This URL of the web service will be like : http://localhost:9001/bncwebservices/v1/electronics/ProductsLocationDetails/eda4b92b-07ab-4ca4-8ecd-43d53123bd98/ Here the only parameter "eda4b92b-07ab-4ca4-8ecd-43d53123bd98" is beacon id. Note: This webservice will return all the products that are associate (i.e. at the same location) with the provided beacon id.
17 | Customize OOB product based web service to return beacon Id and location details of the product along with other OOB product details. | 1.5 | 12 |  |  |  | This will require customization of OOB product webservice (http://localhost:9001/bncwebservice/v1/electronics/products/553637?options=DESCRIPTION) to return product location & beacon Id associate with that product.