## Sheet1
S.No. | Task | Owner | Start Date | End Date | Status | Comments
1 | Create addon "storeActivityAddOn" and install it on bncwebservices | Swarnima/Swapnil | 13/04 | 13/04 | Completed
2 | Create an item "storeActivity" and add following attributes to it. 1. storeId 2. customerId 3. storeVisitDate 4. storeEntryTime 5.storeExitTime 6. timeSpentInStore (save time in minutes, to be calculated only when storeEntryTime and storeExitTime are available) | Swapnil | 13/04 | 13/04 | Completed
3 | Create a web service which will return the status (status:entered/exited) in JSON format URL(/storeActivity) It will receive the following parameters: 1. storeId 2. customerId 3. storeVisitDate | Swapnil | 14/04 | 15/04 | Completed | First there will be a check whether the customer's entry exists, in case it exists and exit time is null in that, then it will calculate the timeSpentInStore and update the same along with the exit time.(as new Date()) In case there is an entry and exit time is not null, also if there is no entry for the customer, then it will create a new entry and save the same along with the entry time (as new Date()) calculate the following field in the controller method timeSpentInStore (save time in minutes, to be calculated only when storeEntryTime and storeExitTime are available)
4 | Create dao, service classes for the above point | Swapnil |  |  | Completed
5 | Create some dummy data for storeActivity itemtype(Impex generation also) | Swapnil | 16/04 | 16/04
8 | Create an item type "beacon" that contains following String type attributes. 1. beaconId 2. majorId 3. minorId | Swarnima | 13/04 | 13/04 | Completed
9 | Create an enumtype BeaconType with following Types 1. Entry 2. Exit 3. Product 4. Checkout | Swarnima | 13/04 | 13/04 | Completed
10 | Create a relation between beacon and BeaconType, a one to many relation(create impex add some dummy data for beacons and relation) | Swarnima | 13/04 | 13/04 | Completed
15 | Create a webservice to return the beacon type in JSON format. The web service will accept the beaconId, majorId, minorId (in JSON format). URL(/beaconType) And it will query and return the type of the beacon | Swarnima | 13/04 | 14/04 | Completed | At the IOS side, we will need to have a link such that, when entry/exit beacon type is found, then they should send the webservice with URL /storeActivity When product beacon type is found then they should send the webservice with URL /popularityCount
16 | Create service and dao classes for the above point | Swarnima |  |  | Completed
11 | Customize product item type by adding following attribute. 1. popularityCount (int type) | Swapnil | 17/04 | 17/04
12 | Create a one to many relation between beacon and products. And add some sample data in it (create impex) | Swapnil | 17/04 | 17/04
13 | Create a webservice to update the popularityCount of the product. The web service will accept the beaconId, majorId, minorId (in JSON format). URL(/popularityCount) Will use the request data to get the product from the relation defined in point above and increase the popularity count for the product. | Swapnil | 20/04 | 21/04
14 | Create service and dao classes to get top 5 popular products based on the popularity count. The count "5" should be made configurable. |  |  |  |  | Make 5 configurable in property file.
17 | extend the existing customer type to add the following attributes to it. 1. weight 2. height 3. Age 4. Gender | Swapnil | 22/04 | 22/04
18 | Create impex to store some sample data in customer for the above point | Swapnil | 23/04 | 23/04
22 | Create an enumtype DeviceTypeCode with 2 values APP001 for Desktop APP002 for Mobile | Swarnima | 15/04 | 15/04 | Completed
23 | Extend the Customer item type to include a new enumtype attribute, deviceTypeCode referring above. Set the default value of the attribute to be APP001 | Swarnima | 15/04 | 15/04 | Completed
24 | Extend the customer related populator and create beans to include the above newly created attribute | Swarnima | 15/04 | 15/04 | Completed
25 | Extend the current login webservice controller to save the deviceTypeCode as "APP002" into Customer when customer logs in. | Swapnil | 24/04 | 27/04
26 | Extend the existing login controller from storefront to save the deviceTypeCode as "APP001" into Customer when customer logs in | Swarnima | 16/04 | 17/04
6 | Create service and dao classes to get most visited stores by customers. The "storeActivity" item (created in step 2) is to be queried to get most visited stores |  |  |  |  | Property file - for showing a 5-6 most visited stores | Impex
7 | Create service and dao classes to get loyal customers. The "storeActivity" item is to be queried to get the customers who visit stores the most |  |  |  |  | Property file - for showing a 5-6 most loyal customers
Create service and dao for retrieving the count of customers logging in from mobile and desktop separately.
19 | Create a WCMS page for the Activity dashboard, impex creation.
20 | Create controller, facades, service classes to fetch model data for store customer profile section (point 11), popular products (based on product popularity count, point 7), most visited stores (point 4), loyal customers (from point 5), spent time (query storeActivity item, point 2)
21 | To get weather information, there are two approaches. 1) The weather data is passed by IOS app, if so we can use it to dispplay on our page. 2) To use java APIs to fetch weather data based on city or zip code. Please see the sample code http://code.aksingh.net/owm-japis/src