## Sheet1
Functionality | Development | UT | AT | IT/ST | TOTAL(hours) | Developer | Start date | End Date | Status
1. Create a new extension named qrcode using yempty as template | 2 |  |  |  | 2 | Swarnima | 2015-07-27 | 2015-07-27 | Completed
2. Separate the items and related code from qrcodeaddon. And add it in the extension created above. |  |  |  |  | 19
a. Move item types | 3 |  |  |  |  | Swarnima | 2015-07-27 | 2015-07-27 | Completed
b. Move data objects | 2 |  |  |  |  | Swarnima | 2015-07-27 | 2015-07-27 | Completed
c. Test and move other related independent classes | 4 | 2 | 2 | 4 |  | Swarnima | 2015-07-28 | 2015-07-31 | In progress
d. Modify dependencies on classes inside qrcodeaddon | 2 |  |  |  |  | Swarnima | 2015-07-28 | 2015-07-31 | In progress
3. Create a new addon "facerecognitionaddon". Install the addon on bncwebservices and storefront | 4 |  |  |  | 4 | Jayasree | 2015-07-24 | 2015-07-24 | Completed
4. Add itemtypes | 4 |  |  |  | 4 | Jayasree | 2015-07-24 | 2015-07-24 | Completed
5. Add data objects through beans.xml | 2 |  |  |  | 2 | Jayasree | 2015-07-27 | 2015-07-27 | Completed
6. Create ImageQualityPopulator with spring configuration | 4 |  |  |  | 4 | Jayasree | 2015-07-27 | 2015-07-27 | Completed
6.a.Create Spring configuration for Customer |  |  |  |  | 16 | jayasree | 2015-07-28 | 2015-07-28 | Completed
7. Add a new CMS page for uploading profile picture with same template as account | 4 | 2 | 2 | 2 |  | Jayasree | 2015-07-27 | 2015-07-27 | Completed
a. Create controller with GET method(MDIYImageQualityCheckController) | 2 |  |  |  |  | Swapnil | 2015-07-27 | 2015-07-27 | Completed
b. Write the JSP to be rendered | 4 |  |  |  |  | Swarnima | 2015-07-27 | 2015-07-31 | In progress(dependent)
c. Create the method saveCustomerDetails which is triggered on load of profile pic | 1 | 2 | 2 | 4 | 22 | Jayasree | 2015-07-28 | 2015-07-28 | Completed
8. Create MDIYCustomerDataFacade
9. Create MDIYCustomerDataFacadeImpl | 4 |  |  |  |  | Jayasree | 2015-07-28 | 2015-07-31 | In progress(dependent)
a.Implement saveCustomerImage() | 2 |  |  |  |  | Jayasree | 2015-07-28 | 2015-07-31 | Completed
b.Implement saveCustomerData() | 1 |  |  |  |  | Jayasree | 2015-07-30 | 2015-07-30 | Completed
10. Create MDIYCustomerDataService
11. Create MDIYSaveCustomerDataServiceImpl | 6 |  |  |  |  | Jayasree | 2015-07-30 | 2015-07-30 | Completed
a. Implement saveCustomerData() |  | 2 | 2 | 2 | 12
12. Create a new webservice controller MDIYImageUploadByMobileController | 4 |  |  |  |  | Jayasree | 2015-07-30 | 2015-07-31 | In progress(dependent)
a. Create saveCustomerDetails() | 2 |  |  |  |  | Jayasree | 2015-07-30 | 2015-07-31 | In progress(dependent)
b. Create getCustomerDataFromJsonString() | 2 |  |  |  |  | Jayasree | 2015-07-30 | 2015-07-31 | In progress(dependent)
c. Create populateCustomerData() | 4 |  |  |  | 17 | Jayasree | 2015-08-03 | 2015-08-03 | In progress(dependent)
13. Add method persistNewUser to existing controller MDIYImageQualityCheckController | 1 | 2 | 2 | 2 |  | Jayasree | 2015-08-03 | 2015-08-03 | Completed
14. Create MDIYSaveBiometricDataFacade
15. Create MDIYSaveBiometricDataFacadeImpl | 2 |  |  |  |  | Jayasree | 2015-08-03 | 2015-08-03 | Completed
a. Declare variables and methods | [5 empty] | Jayasree | 2015-08-04 | 2015-08-04 | Completed
b.Implement saveBiometricData() | 1 |  |  |  |  | Jayasree | 2015-08-04 | 2015-08-04 | completed
16. Create MDIYSaveBiometricDataService
17. Create MDIYSaveBiometricDataServiceImpl | 3 |  |  |  |  | Jayasree | 2015-08-04 | 2015-08-04 | completed
a.implement saveBiometricData() | 6 | 2 |  | 2 | 10 | Jayasree | 2015-08-05 | 2015-08-05
18. Create cronjob MDIYPersistUserCronJob | [6 empty] | 2015-08-06 | 2015-08-07
|  | 2 | 2 | 4 | 31
19. Create Controller MDIYSubmitUserController | 3 |  |  |  |  | Swarnima | 2015-08-03 | 2015-08-03
a. Declare variables and methods
| 1 |  |  |  |  | Swarnima | 2015-08-03 | 2015-08-03
20. Create MDIYSubmitUserFacade
21. Create MDIYSubmitUserFacadeImpl | 4 |  |  |  |  | Swarnima | 2015-08-03 | 2015-08-03
a.Implement addUserToQueue() | 1 |  |  |  |  | Swarnima | 2015-08-04 | 2015-08-04
22. Create MDIYSubmitUserService
23. Create MDYSubmitUserServiceImpl | 3 |  |  |  |  | Swarnima | 2015-08-04 | 2015-08-04
a.Implement addUserToQueue() | 1 |  |  |  |  | Swarnima | 2015-08-04 | 2015-08-04
24. Create MDIYSubmitUserDao
25. Create MDYSubmitUserDaoImpl | 3 |  |  |  |  | Swarnima | 2015-08-04 | 2015-08-04
a.Implement doesCustomerExist() | 3 |  |  |  |  | Swarnima | 2015-08-05 | 2015-08-05
26. Create MDIYCSRCustomerPopulator | 4 |  |  |  |  | Swarnima | 2015-08-05 | 2015-08-06
27. Create MDIYImagePopulator
9
Configuration
150
Total