## Tasks
S.No | Task description | Effort (days) | Start Date | End Date | Owner | Comments/Assumptions | Status
1 | New module creation (b2c) (name : QRScanner) | 0.5 | 2014-11-03 | 2014-11-03 | All | Download latest Hybris 5.3 and create new b2c module "QRScanner" + Ant clean all + Init + Host files entry | Completed
2 | CSR Login page | 1.5 | 2014-11-03 | 2014-11-03 | Swarnima | Just like BnC , CSR login page implementation is required here ( proper user group needs to be created) | Completed
3 | Addition of CSR Login link on the OOB Header of the storefront | 0.5 | 2014-11-03 | 2014-11-03 | Swapnil | Entry point for CSR to login. Create impex to add this link on the header component. | Completed
4 | Data modeling for new field UCOID | 0.5 | 2014-11-03 | 2014-11-03 | Prasun | Add this new field in Database + Hybris Update | Completed
5 | Data modeling for new itemtype: collectOrder (This will manage the queue for list of orders that needs to be packed and collected from counter) | 0.5 | 2014-11-04 | 2014-11-04 | Prasun | This type will have 5 attributes (1) CID, (2) OID, (3) UCOID, (4) PID, (5) Status. --> CID: Customer Id --> OID: Oder Id --> UCOID: Our new field --> PID: Product Id --> Status: Product collection status (PENDING/COMPLETED) | Completed
6 | Customize OOB Delivery method page and provide option to choose the "Pick up from next counter" option. | 1 | 2014-11-04 | 2014-11-05 | Prasun | Add new filed/drop down for "Pick up from next counter" + Hybris update + UI Changes. Also add a check that UCOID code will be generated (and will be added in queue) only when user has slected this option of delivery else its OOB. | Completed
7 | Utility class for creating UCOID(encrypted unique customer & order identifier [UCOID] on the fly based on order id, customer id, Date and Time of placing Order) | 1.5 | 2014-11-05 | 2014-11-06 | Swarnima | Complete code logic to generate and save UCOID. | Completed
8 | Interceptor class for calling and retrieving the generated UCOID from Utility class and saving the value in Order Model. | 1 | 2014-11-06 | 2014-11-07 | Swarnima |  | Completed
9 | Complete code logic to capture & save the values in "collectOrder" table (i.e. when customer who choose to collect the order places the order and when CSR agent completes the order) | 1 | 2014-11-07 | 2014-11-10 | Prasun | It is through this table the queue for order (that needs to be collected) will be managed by CSR agent, hence it needs to be updated every time with latest values. | Completed
10 | Customize Thank you page to show UCOID along with order details. | 0.5 | 2014-11-07 | 2014-11-07 | Swapnil | If the UCOID is generated than it needs to be shown on Thankyou page. Once the order is marked as complete the message should be promped to the customer to collect the order from the next counter/billing desk. On order confirmation page, UCOID is to be displayed to the customer(along with a message to not share it with anyone.) | Completed
11 | CSR Landing page to show last 5 orders ( configurable) that are pending for package & collection. | 1.5 | 2014-11-07 | 2014-11-10 | Swarnima | This will be CSR page for displaying orders placed (based on delivery Mode : Pick up from next counter) in tabular format(auto-refresh along with a refresh button) | Completed
12 | HTML integration for this CSR Landing page | 1 |  |  | Swapnil/Swarnima | Assuming HTMLs will be provided by UI team.
13 | CSR agent should have option to see all the pending orders, i.e. if more than 5 orders are pending then "Show more" link should be provided that will expand the table to show all pending order ( pagination if required) | 1.5 | 2014-11-11 | 2014-11-12 | Swapnil | Use Hybris OOB pagination feature (if required). | Completed
14 | CSR agent should have option to search the pending order details through UCOID. | 1 | 2014-11-12 | 2014-11-13 | Swapnil |  | Completed
15 | The pending order detail page should show all the details of the order & customer | 1.5 | 2014-11-11 | 2014-11-12 | Swarnima | Also on click of UCOID, This order details shall be opened along with status change drop-down (submit on value change). | Completed
16 | After marking the order as complete , the status should change in "collectOrder" table | 1 | 2014-11-12 | 2014-11-13 | Swarnima |  | Completed
17 | After the order is collected it should get removed from the pending order ( by changing the status to complete) | 1 | 2014-11-13 | 2014-11-14 | Swarnima | Order status to be updated on the order confirmation page(auto-refresh along with a refresh button)
18 | On the customer My Account create a Order Collect History page ( similar to OOB Order History page) showing the current staus of the order i.e. Pending or Complete (ready to be collected from counter). | 2 | 2014-11-11 | 2014-11-12 | Prasun |  | Completed
19 | Modify order list page related jsps Create same for mobile also | 1 | 2014-11-20 | 2014-11-20 | Swarnima | Integrate with HTML code. (index.html and css and javascripts) | Completed
20 | Modify back end functionality for order listing | 1 | 2014-11-21 | 2014-11-21 | Swarnima | 1)Remove dependency on template 2)Retrieve CSR Agent's name to show on the JSP 3)Retrieve CollectOrders Created Time Stamp in the format HH:MM AM/PM 4)Retrieve the orders statistics : 1. Queued Orders - Status as PENDING 2. Active Orders - Status as COMPLETED 3. Serviced Orders - Status as COLLECTED 4. Target - for now assuming (no. of serviced orders/total collected orders placed)*100 | Completed
21 | Modify orderDetailsPage.jsp Create same for mobile as well. | 1 | 2014-11-21 | 2014-11-21 | Swapnil | Create fragment JSPs for order details.(desktop and mobile)(JSON format)(for now basic UI as HTML code is not available for order details yet) | Completed
22 | Create functionality for retrieving orders based on Date and Time. | 1 | 2014-11-24 | 2014-11-24 | Swarnima | Use createdTS attribute to compare. Integrate it with Time Search on ordersListPage.jsp | Completed
23 | Create a Sound Notification when new order is placed on CSR Dashboard | 1 | 2014-11-25 | 2014-11-25 | Swarnima | Add functionality for: 1. Auto Refresh the order listing(blue area only) after every 30 sec through AJAX 2. If new orders are returned through the AJAX(30 sec time interval query) , then Add more divs for the new orders below the orders list 3. Simultaneously play a notification sound 4. Simultaneously Increase the count on the bell icon as per the number of orders | Completed
24 | Create a sound notification when a new customer enters the store. | 1 | 2014-11-25 | 2014-11-26 | Prasun | 1. Auto refresh through AJAX 2. If new customers are returned through AJAX(5 sec time interval query), add more divs for the new customers below the waiting for assistance list. 3. Simultaneously play a notification sound | Completed
25 | Change the logic of existing BNC webservice to incorporate uuid as beacon id and not as unique user id. | 1 | 2014-11-21 | 2014-11-24 | Prasun | This is done to add users in pending CSR queue based on beacon id and hence it will remove the hard coded dependency on uuid which was previously assumed to be unique user id. | Completed
26 | Change comments on the order confirmation page and Order History Page | 0.5 | 2014-11-25 | 2014-11-25 | Prasun | Add the comments - "Kindly collect your order from Aisle 10" | Completed
27 | Create IMPEX to map all the unique devide Ids with the already existing customers in the hybris database. | 1 | 2014-11-25 | 2014-11-26 | Prasun | IMPEX should create the customers also. | Completed
28 | Integrate Order Details UI with the available HTML code | 2 | 2014-11-25 | 2014-11-26 | Swapnil | Kindly consider all points : 1. All products in tabular format along with their images, quantities, unit price and total price 2. Dropdown for changing the order status - Use the same functionality existing with the previous UI. 3. Ignore the check boxes | Completed
| Integrate Customer Details for the order with the available HTML code |  |  |  |  | 1. Customer details along with their image 2. Also show the recently viewed products (create JSP or tag of the existing corresponding component.jsp, and add the supporting code of the component controller in the new controller.) 3. Also show the wishlist products (create JSP or tag of the existing corresponding component.jsp, and add the supporting code of the component controller in the new controller.) 4. Ignore the Assist Button for now 5. Also ignore the Shopping Trend for now
29 | Integrate new Customers Landing Page UI with existing code | 1 | 2014-12-08 | 2014-12-08 | Swarnima | Customers Dashboard UI Integration as per personal_data.html with following changes(modify the customerDetailsPage.jsp): 1. Add buttons - Send Greeting, Assist, No Thanks on the top as per send_greetings.html 2. Show the top customer as selected by default with their details on right side 3. Status monitoring to be done as per enumtype CSRStoreStatus, with LoggedIn as Queued, InService as Active, Completed as Serviced. 4. The Queued page has to show the LoggedIn status customers for the day. 5. Changes in methods in DAO, Services, Facades, Controllers as required. 6. Create proper tags for the same instead of everything to be on one JSP. 7. Remove dependency on template | Completed
30 | Implement search by customer name functionality | 1.5 | 2014-12-08 | 2014-12-09 | Swapnil | Implement the Search functionality similar to the UCOID search in the orders dashboard. Search has to be based on Customer name.(AJAX Search) Also, the first customer should be shown as selected by default and his details on the right panel Create methods for searching the CSRCustomerDetails table by customerName in Dao, Facade, Service, Controller. | Completed
31 | Chart Navigation and their count to be made dynamic | 0.5 | 2014-12-09 | 2014-12-09 | Swarnima | The chart has to be made as navigation, and their counts to be properly updated. On their respective clicks, the status as per LoggedIn as Queued, InService as Active, Completed as Serviced to be shown Also, by default the first customer has to be shown as selected and their details on the right panel. | Completed
32 | Implement the Active Page functionality | 0.5 | 2014-12-09 | 2014-12-09 | Swarnima | 1. On Active Tab, display the list of CSRCustomerDetailsModel which are InService status. 2. Also, show at the bottom of the Customer Name, "assisted by <AGENT NAme>" 3. Show only Serviced Button on the right panel, and this button should be visible only to the CSR agent who is assisting the customer | Completed
33 | Implement the Serviced Page functionality | 0.5 | 2014-12-10 | 2014-12-10 | Swarnima | 1. On Serviced Tab, display the list of CSRCustomerDetailsModel which are in COMPLETED status. 2. Also, show at the bottom of the Customer Name, "assisted by <AGENT NAme>" 3. Show no button on the right panel. | Completed
34 | Implement the Date Time Search | 1 | 2014-12-09 | 2014-12-10 | Swapnil | Implement the Date Time Search similar to the one implemented for orders dashboard with new methods for the same in DAO, Services, Facades, Controllers.(AJAX Search) Also, the first customer should be shown as selected by default and his details on the right panel | Completed
35 | Implement the Assist Button functionality | 0.5 | 2014-12-10 | 2014-12-10 | Swarnima | Implement the functionality of Assist Button. On click of the button, the CSRStoreStatus of the CSRCustomerDetails should change to InService status. UI wise, check that the customer details are no longer shown on the Queued Page and should be shown on the Active Page. | Completed
37 | Implement the Serviced Button functionality | 0.5 | 2014-12-10 | 2014-12-10 | Swapnil | Implement the functionality of Serviced Button. On click of the button, the CSRStoreStatus of the CSRCustomerDetails should change to Completed status. UI wise, check that the customer is no longer shown on the Active Page and should be shown on the Serviced Page | Completed
36 | On click of customer names on the left panel, their corresponsing details should be opened on the right panel. | 1 | 2014-12-11 | 2014-12-11 | Swarnima | On click of customer names on the left panel, their corresponsing details should be opened on the right panel. Also show the customer name as selected on the left panel. | Completed
38 | Add Order history, Recommended Products, Recently Viewed Products and Wishlist on the customer details page | 1 | 2014-12-11 | 2014-12-11 | Swarnima | Add Order history, Recommended Products, Recently Viewed Products and Wishlist on the customer details page Add JSPs from the components and as done previously for the customer details for orders dashboard with similar changes in controller. | Completed
39 | Implement Send Greeting functionality. | 1 | 2014-12-12 | 2014-12-12 | Swarnima | Implement Send Greeting functionality. 1. A text window has to be shown on clicking the Send Greeting button. 2. The text window should show some default Text, and must be editable by the CSR agent. 3. On click of Send Button, an email should be sent to the customer on their email id. for now assume the email from id to be as customerservicebnc@hybris.com 4. On click of cancel button the text window should close. | Completed
40 | The notification bell count and ajax refresh of queued customers | 0.5 | 2014-12-12 | 2014-12-12 | Swarnima | The notification bell should show the count equal to number of queued customers. Page must be refreshed through AJAX every 60 seconds. With every new addition of customer in queued list, a sound should be played. | Completed
41 | Create an addon "qrcodeaddon" for the bnc scenario 1. Copy existing code from bnc extensions into qrcodeaddon | 1 |  |  |  | Create an addon "qrcodeaddon" for the bnc scenario 1. Copy existing code from bnc extensions into qrcodeaddon | Completed
42 | Create Impexes: 1. for modifying existing product template with the addon template(desktop and mobile) 2. for creating and assigning the ucoid component on order confirmation page(desktop and mobile) 3. for new content slots for components on pages(desktop and mobile) 4. for creating and assigning new cmsparagraphcomponent on pages(desktop and mobile) 5. For creating CSR Login link in Header links | 3 |  |  |  | Create Impexes: 1. for modifying existing product template with the addon template(desktop and mobile) 2. for creating and assigning the ucoid component on order confirmation page(desktop and mobile) 3. for new content slots for components on pages(desktop and mobile) 4. for creating and assigning new cmsparagraphcomponent on pages(desktop and mobile) 5. For creating CSR Login link in Header links | Completed
43 | Separate impexes with respect to their functionalities | 0.5 |  |  |  | Separate impexes with respect to their functionalities | Completed
44 | Add AddToWishlist code in mobile JSPs | 0.5 |  |  |  | Add AddToWishlist code in mobile JSPs | Completed
45 | Add property messages to the addon | 0.5 |  |  |  | Add property messages to the addon | Completed
46 | Add recommendations in the addon | 1 |  |  |  | Add recommendations in the addon | Completed
47 | Add collect orders interface code in my account for user Add component, impex | 1 |  |  |  | Add collect orders interface code in my account for user Add component, impex | Completed
48 | Separate the code of recently viewed products from Product Page controller. Create ajax request, controller. | 1 |  |  |  | Separate the code of recently viewed products from Product Page controller. Create ajax request, controller. | Completed
49 | Hook into init/update process for importing impexes automatically. | 1 |  |  |  | Hook into init/update process for importing impexes automatically. | Completed
50 | Test the addon with a new module | 2 |  |  |  | Test the addon with a new module | Completed
51 | Create document for installing the addon. And add the addon code in a zipped file to GITHUB | 1 |  |  |  | Create document for installing the addon. And add the addon code in a zipped file to GITHUB | Completed

## Defects
S.No | Defect description | Effort (days) | Start Date | End Date | Owner | Status
1 | Queued and active pages to show all orders irrespective of date and time criteria on first load |  |  |  |  | Closed
2 | Delivery method to show Aisle 10 instead of next counter |  |  |  |  | Closed
3 | Proper dates check for date time search functionality(e.g. From date entered should be before to date check) |  |  |  |  | Closed
4 | Enabled To time input field for the active and serviced pages |  |  |  |  | Closed
5 | Auto refresh time changed from 30 secs to 1 minute |  |  |  |  | Closed
6 | Cart items missing- cart entries were missing , showing order entries directly from order instead of from consignment. |  |  |  |  | Closed
7 | CSS issue with drop down – Shifted arrow to the left as it was overlapping the text |  |  |  |  | Closed
8 | Remove the checkbox, as its not implemented |  |  |  |  | Closed
9 | The side bar should not exceed the limit( red line). |  |  |  |  | Closed
10 | The links in the side bar are not working. – Enabled Customers Dashboard and Orders dashboard links |  |  |  |  | Closed
11 | Dim the unimplemented links. They can be left on the side bar, but let there be a distinction between implemented and unimplemented links. |  |  |  |  | Closed
12 | Side bar should become visible only when clicked on side menu link. |  |  |  |  | Closed