## Sheet1
S.No. | Task | Owner | Start Date | End Date | Status | Comments
1 | Create addon "storeActivityAddOn" and install it on bncwebservices | Swarnima/Swapnil | 18/03 | 18/03
2 | Create an item "storeActivity" and add following attributes to it. 1. storeId 2. customerId 3. storeVisitDate 4. storeEntryTime 5.storeExitTime 6. timeSpentInStore (save time in minutes, to be calculated only when storeEntryTime and storeExitTime are available) | Swapnil | 18/03 | 18/03
3 | Create a web service that takes following prameters in JSON format. 1. storeId 2. customerId 3. storeVisitDate 4. storeEntryTime 5.storeExitTime 6. timeSpentInStore (save time in minutes, to be calculated only when storeEntryTime and storeExitTime are available) | Swarnima | 18/03 | 20/03
4 | Create service and dao classes to get most visited stores by customer. The "storeActivity" item is to be queried to get most visited stores | Swapnil | 18/03 | 19/03
5 | Create service and dao classes to get loyal customers. The "storeActivity" item is to be queried to get the customers who visit stores the most | Swapnil | 19/03 | 20/03