## Sheet1
S.No | Task description | Effort (days) | Effort (hours) | Start Date | End Date | Owner | Comments/Assumptions | Status
0 | Create Addon named "healthpromotionsaddon" | 0 | 0 | 2015-01-08 | 2015-01-08 | Swarnima / Swapnil | Create a separate functionality altogether. Including bncwebservices | Completed
1 | Impex to create new category "Health Products" in existing electronics store catalog. | 0.5 | 4 | 2015-01-08 | 2015-01-08 | Swapnil | This category will hold all the new health related products (Note: Since all these are elecronic products we will keep it under electronics catalog). | Completed
2 | Add all the required permissions to this new category so that its accessible by relevant user groups. | 0.5 | 4 | 2015-01-08 | 2015-01-08 | Swapnil | After above steps & hybris update verify that new products have been added in database and are accessible on PDP pages etc. | Completed
3 | Impex to import health product data (and Image) in database. Assumption: Image is provided by UI team. | 3 | 24 | 2015-01-09 | 2015-01-22 | Swarnima / Swapnil | Create following impex to import the new health related electronics products in database. (1) product.impex (2) products-media.impex (3) products_en.impex (4) products-prices.impex (5) products-relations.impex (6) products-stocklevels.impex (7) warehouses.impex | Completed
4 | Create a new data model for managing health related customer data. | 0.5 | 4 | 2015-01-08 | 2015-01-08 | Swarnima | This new data model "CustomerHealthData" should have following fields: (1) Heart beat rate (2) Blood Pressure (3) Miles run (4) Calories burned (5) Time taken (6) Age (7) CustomerId | Completed
5 | Create web service to get all the customer exercise data (heartbeat, blood pressure, miles, calories, time, age) through url of the web service. | 1.5 | 12 | 2015-01-08 | 2015-01-09 | Swarnima | The web service will be accessible through following URL. http://localhost:9001/bncwebservices/v1/electronics/CustomerHealthData The values shall be passed as a JSON object as follows: {‘HealthData’: [ {‘type’: ‘customerId’, ‘Value’ : ‘123’}, {‘type’: ‘heartbeatrate’, ‘Value’ : ‘72’}, {‘type’: ‘bloodPressure’, ‘Value’ : ‘80’} ] } and so on.. The significance of values are as follows: 60 - Heart beat per minute 100 - blood pressure (mmHg) 1.5 - Miles run 150 - Calories burned 30 - minutes 29 - Age | Completed
6 | Implementation of backend logic to save all the data retrieved from web service in database. | 1 | 8 | 2015-01-19 | 2015-01-19 | Swarnima | This will involve façade, service, dao layer etc. | Completed
7 | Create a new item type "beacon" having following attributes: 1.) Id 2.) MajorId 3.) MinorId 4.) Welcome Message | 0.5 | 4 | 2015-01-21 | 2015-01-21 | Swarnima | This will hold data for all beacon including its major & minor Id. | Completed
8 | Create a N-N relation between "beacon" and "AbstractPromotions" | 0.5 | 4 | 2015-01-21 | 2015-01-21 | Swarnima | This relation is required because multiple promotions can be associated with one beacon and at same time one promotion can be associated with multiple beacon also, hence N-N relation. | Completed
9 | Create few promotions and beacon instances through HMC and associate the promotions with beacon instances so created. Note: Create Impex for the same. | 0.5 | 4 | 2015-01-22 | 2015-01-22 | Swapnil | This is to be done through HMC. The idea is to have multiple instances of promotions and beacon present in the database so that the promotional webservice could retrieve the same. | Completed
10 | Create promotional web service specific to beacon id. | 2.5 | 20 | 2015-01-22 | 2015-01-27 | Swarnima | This URL of the web service will be like : http://localhost:9001/bncwebservices/v1/electronics/BeaconPromotions/eda4b92b-07ab-4ca4-8ecd-43d53123bd98/000001/000002 Here "eda4b92b-07ab-4ca4-8ecd-43d53123bd98" is beacon id, "000001" is major Id and "000002" is minor Id. Note: This webservice will return the welcome message and all the promotions associated with this beacon id. Example : Welcome Message :=> Welcome to our Store! 30 % off on Digital cameras for today only. Promotions :=> 1.) Buy one get one free. 2.) Get SD card free with Samsung mobiles. | Completed
11 | Create few promotions and assign a relevant user group (having your target customer) to it. Note: Create Impex for the same. | 1 | 8 | 2015-01-22 | 2015-01-23 | Swapnil | This is customer specific promotion so beaconId need not be present here. The idea is to group the target customers based on there health data and then offer promotions to them. Example: All the customers who run more than 1 Mile per day can be offered discount on sports shoes. | Completed
12 | Create one more promotional web service specific to the customer. This will return all the promotions that are applicable for the user group of this user. | 2.5 | 20 | 2015-01-23 | 2015-01-28 | Swapnil | This URL of the web service will be like : http://localhost:9001/bncwebservices/v1/electronics/CustomerHealthPromotions/neeraj.a.shah@accenture.com Here the only parameter "neeraj.a.shah@accenture" is the unique email id of the user. Note: This webservice will return all the promotions associated with the mention user. | Completed
13 | Create a cron job to send mails to the customers who are eligible for promotions. | 2.5 | 20 | 2015-01-27 | 2015-01-29 | Swarnima | This will involve new entry in item.xml, spring.xml, extension of job performable class and implementation of perform method() having logic to retrieve all the customers that are eligible for promotions. Note: It will internally use above mention web service to check for the promotions based on customer Id. | Completed
14 | Triggering emails to the customer. | 2 | 16 | 2015-01-30 | 2015-02-02 | Swarnima | This will involve setting up SMTP server , setting up mail templates and then triggering mail to the customer with the relevant promotion information retrieved from the above web service. | Completed
15 | Extend the Product data model to add "beaconId" and "location" attributes. | 0.5 | 4 | 2015-01-29 | 2015-01-29 | Swapnil | This is done to associate products with beacon id and to store location of the products . (location will be seprated by ‘¦’ character e.g. Aisle 2B¦Wing 4¦Floor 3) | Completed
16 | Create Impex to insert beaconId and location data in the product table. | 0.5 | 4 | 2015-01-29 | 2015-01-29 | Swapnil | This data will be used by relevant web services. | Completed
17 | Create web service to retrieve all the product details (location etc) depending on the beacon id. | 2 | 16 | 2015-01-30 | 2015-02-02 | Swapnil | This URL of the web service will be like : http://localhost:9001/bncwebservices/v1/electronics/ProductLocationDetails/eda4b92b-07ab-4ca4-8ecd-43d53123bd98/ Here the only parameter "eda4b92b-07ab-4ca4-8ecd-43d53123bd98" is beacon id. Note: This webservice will return all the products that are associate (i.e. at the same location) with the provided beacon id. | Completed
18 | Customize OOB product based web service to return beacon Id and location details of the product along with other OOB product details. | 1.5 | 12 | 2015-02-03 | 2015-02-04 | Swapnil | This will require customization of OOB product webservice (http://localhost:9001/bncwebservices/v1/electronics/products/553637?options=DESCRIPTION) to return product location & beacon Id associate with that product. | Completed

## Defects
S.No | Defect description | Effort (days) | Start Date | End Date | Owner | Status | Comments
1 | OOB products and category pages not opening - 404 not found error |  |  |  | Swarnima | Closed
2 | Send UCOID along with the other order details through in existing webservice |  |  |  | Swarnima | Closed
3 | Change the return type of Beacon webservice to JSON |  |  |  | Swarnima | Closed
4 | Customer Health Data webservice not recognising the customer. Showing customer not found. |  |  |  | Swarnima | Closed
5 | Products are not adding to recently viewed list when viewed from the mobile application |  |  |  | Swapnil | Closed
6 | Existing UI fixes:
7 | Remove dependency on bncstorefront for dummy images for customers showing on csr dashboard |  |  |  | Swarnima | Closed
8 | Image size fix for left navigation |  |  |  | Swarnima | Closed
9 | Change the bell shound for both Customers and Orders Dashboard |  |  |  | Swapnil | Closed
10 | Carousel functionality for wishlist, recently viewed and recommended products not working. |  |  |  | Swarnima | Closed
11 | Align customer details properly on personal page on orders dashboard |  |  |  | Swarnima | Closed
12 | % sign not showing in target |  |  |  | Swapnil | Open
13 | Pie charts not working for dynamic values. Charts are showing only when we hardcode the values in the JSP. |  |  |  | Senthil | Open | As a temporary solution, we have implemented the Old UI charts for the demo. But we need to look into this.
14 | The UI is not responsive. |  |  |  | Senthil | Open | Distorted on Ipad
15 | The Header left navigation remains open on ipad |  |  |  | Senthil | Open
16 | The right hand hovering menu for signing out a CSR Agent is not opening on ipad |  |  |  | Senthil | Open
17 | Only 1 customer is shown on the left navigation even when there are more than 1 customers. The other customer appears only when the first one has been removed from the queue. |  |  |  | Swarnima | Closed
18 | Move the assist/Serviced/No Thanks button up right next to the customer's image and below the customer's name |  |  |  | Swapnil | Closed
19 | The whole page should not refresh, only the required divs should refresh, a. the left nav section for customers/orders b. the charts c. if required the right section also. |  |  |  | Swarnima | Closed
20 | Change the beacon item type and make the beaconid, majorId and minorId unique attributes. Also test with the impexes to see whether beacon with same beaconId and different major and minor Ids are being saved to the database. |  |  |  | Swapnil | Closed
21 | The accordion on order history tab overlaps the order details with other accordion tabs |  |  |  | Swapnil | Open
21 | Regarding the promotions notifications showing on IOS App - The welcome message is coming as heading for the promotions. We need to show the welcome messages separately |  |  |  | IOS App | Open
21 | Regarding the promotions notifications showing on IOS App - On click of the promotions, it is redirecting to HAC as the URL at the back end of the promotions is wrong. We need to remove the url on click of the promotions, Instead we can show the alert type pop-up on click of the promotions, which will show the full promotions message with code and validity |  |  |  | IOS App | Open
21 | The promotions are only showing when the customer is logged into the IOS App. Need to fix this as it should show the promotions even when the customer is not logged in, as we will be using the device id to recognise the promotions list. |  |  |  | IOS App | Open
21 | The categories names seems to be hardcoded in the IOS App. It should be dynamic based on the category code |  |  |  | IOS App | Open
21 | The health products category is not showing on the IOS App. |  |  |  | IOS App | Open

## Addtnl Tasks
S.No | Defect description | Effort (days) | Start Date | End Date | Owner | Explanation | Status
1 | Create a new webservice for detecting a beacon and performing 2 tasks - showing promotions and welcome messages, and adding customer to the waiting queue Merge the 2 existing webservices for beacon detection in 1 |  |  |  | Swarnima |  | Completed
2 | Integration of new UI |  |  |  | Swarnima/Swapnil |  | Completed
3 | Change the return type of Customer Health Data webservice to JSON |  |  |  | Swarnima |  | Completed
4 | Create a new webservice for retrieving all the beacon ids and their major and minor ids |  |  |  | Swapnil |  | Completed
5 | Create a new webservice for retrieving all the customer's collect orders |  |  |  | Swarnima |  | Completed
6 | Add the additional Customer Health Data attributes and modify related code for the saving the health data for the customer |  |  |  | Swapnil |  | Completed
7 | Move the default beacon and their major and minor ids to properties file(the beacon which adds the customer to the waiting queue) for easy change in future |  |  |  | Swarnima |  | Completed
8 | Create webservice for sending all wishlist products for the customer. | 1.5 | 2015-03-02 | 2015-03-03 | Swarnima | This webservice will receive the JSON object as {"uid":"sdsf@cccccbc.com"} And it will send the ProductDataList The URL of the webservice will be: http://localhost:9001/bncwebservices/v1/electronics/wishlist/get | Completed
9 | Create webservice for adding a product to the wishlist for a customer | 1 | 2015-03-03 | 2015-03-04 | Swarnima | This webservice will receive the JSON object as {"uid":"sdsf@cccccbc.com","productId":"4567"} And it will send the ProductDataList The URL of the webservice will be: http://localhost:9001/bncwebservices/v1/electronics/wishlist/add | Completed
10 | Create webservice for removing a product from the wishlist for a customer | 1 | 2015-03-03 | 2015-03-04 | Swapnil | This webservice will receive the JSON object as {"uid":"sdsf@cccccbc.com","productId":"4567"} And it will send the ProductDataList The URL of the webservice will be: http://localhost:9001/bncwebservices/v1/electronics/wishlist/remove | Completed
11 | Modify the beacon promotions webservices, to send out the promotions based on the customer's and beacon's promotions groups | 1 | 2015-03-04 | 2015-03-05 | Swarnima | Modify the beacon promotions webservices, to send out the promotions based on the customer's and beacon's promotions groups(with no duplications) | Completed
12 | Change the orders dashboard UI with the new one. | 2 |  |  | Swarnima | Will wait till the new UI is made responsive | On Hold
13 | Change the customerhealthdatawebservice to send out the promotions after saving the customer's health details. Take reference from WebserviceFactoryController for sending out the list of promotions. While saving the customer's health data, also assign the promotions to the customer based on some conditions. The conditions should be as follows: Create some sample promotions. Check if the heart rate, or miles run are greater than some value, then assign the related promotions to the customer. | 2 | 2015-04-03 | 2015-04-06 | Swapnil | keep the threshold values in local.properties.
|  |  | 2015-05-13 | 2015-05-18 | Swarnima | Do research and document on ranges forlight rain, moderate rain, heavy rain, sunny, cloudy, light snow, moderate snow, heavy snow weather. After research lets discuss on the ranges needed for identifying the weather clearly. Based on that we will add the properties for min-max range in local.properties. | Completed
|  |  | 2015-05-13 | 2015-05-14 | Swapnil | Add an attribute in the AbstractPromotions itemtype named condition - String type. | Completed
|  |  | 2015-05-13 | 2015-05-14 | Swapnil | Make related changes for populator and add attributes in existing data object. | Completed
|  |  | 2015-05-14 | 2015-05-15 | Swapnil | Create promotions impex with entry for the light rain, moderate rain, heavy rain, sunny, cloudy, light snow, moderate snow, heavy snow weathers. Leave out the beacons details in the impex for those promotions | Completed
|  |  | 2015-05-13 | 2015-05-13 | Swarnima | Create a new itemtype Greeting with 2 attributes: 1. message - String 2. condition - String | Completed
|  |  | 2015-05-13 | 2015-05-15 | Swarnima | Create an impex for the above itemtype. With message and condition should be like light rain, moderate rain, heavy rain, sunny, cloudy, light snow, moderate snow, heavy snow. | Completed
|  |  | 2015-05-14 | 2015-05-15 | Swarnima | Create related Dao, Service and Façade classes for the above itemtype. | Completed
|  |  | 2015-05-14 | 2015-05-15 | Swarnima | Create 3 attributes in Customer Itemtype. Latitudes and Longitudes, Date - type List of Strings and List<Date> | Completed
|  |  | 2015-05-14 | 2015-05-15 | Swarnima | Make related changes for populator and add attributes in existing data object. | Completed
14 | The webservice to send all beacons uuid has been implemented in Hybris. Now this has to be linked in IOS app such that the app should only detect the beacons which have the uuids returned by the webservice. |  | 2015-05-15 | 2015-05-15 | Swapnil | Create a new webservice which will retrieve the latitude and longitude from the IOS App. The URL would be /getGeoLocation Method would be POST The request body should be in the following format: { "lat":"12.32", "long":"10.23", "customerId":"example@email.com" } Find the customer based on the ID. The values should be saved in the Customers Table against the attributes created above. with the condition that if the details already exist in the last entry then not to save the data. | Completed
|  |  | 2015-05-15 | 2015-05-18 | Swarnima | Create a new webservice and combine the code of the above web service which will execute a webservice URL as follows to get the weather information: http://api.worldweatheronline.com/free/v2/weather.ashx?q=45%2C-2&format=json&num_of_days=1&date=today&fx=no&mca=no&fx24=no&includelocation=yes&show_comments=yes&showlocaltime=yes&key=61c3cc6652f35c4e318b62ff3b196 The query in bold is the latitude and longitude in URL format separated by COMMA(,) From the result we receive after hitting the URL, we will retrieve 4 key values from the response: 1. temperature 2. Humidity 3. CloudCover 4. Precipitation(mm) Next based on some conditions, after identifying the climate, it will retrieve the promotions and greetings based on the climate. The final response of the webservice would include(in BeaconPromotionsData): 1. Greeting as welcome message 2. Promotions as List of promotionsdata URL : /greetCustomer POST | Completed
|  |  | 2015-05-18 | 2015-05-18 | Swapnil | Create CustomersGeoData in beans.xml with Data and String as attributes. | Completed
|  |  | 2015-05-19 | 2015-05-19 | Swarnima | Inside CustomersListController, create a new ajax method. Retrieve the list of lat/long/date from customers table. In the loop, execute a webservice which will give the zip, country, state, city with latitude and longitude(in this order) as inputs as follows http://api.wunderground.com/auto/wui/geo/GeoLookupXML/index.xml?query=37.76834106,-122.39418793 From Output we need to consider only following fields: <country>US</country> <state>CA</state> <city>San Francisco</city> <zip>94107</zip> Add these values as San Francisco, 94107 CA, US in a String and save in the CustomersGeoData object along with the date(from the List<Date> for the same index.) Add this List<CustomersGeoData> to the model. | Completed
|  |  | 2015-05-18 | 2015-05-19 | Swapnil | Inside the same controller method, retrieve the latest entry from List of latitudes and longitudes. Using this entry execute the URL for finding out the weather: http://api.worldweatheronline.com/free/v2/weather.ashx?q=45%2C-2&format=json&num_of_days=1&date=today&fx=no&mca=no&fx24=no&includelocation=yes&show_comments=yes&showlocaltime=yes&key=61c3cc6652f35c4e318b62ff3b196 From the result, we will consider onlyt the following 4 fields: 1. temperature 2. Humidity 3. CloudCover 4. Precipitation(mm) Based on a few conditions, as used in the above webservice, identify the climate as a String Add the latitude, longitude and Climate to the model. | Completed
|  |  | 2015-05-20 | 2015-05-21 | Swarnima | Integrate the HTML of "Geo Location" tab with the existing code as per the code sent by Senthil. Create this as a fragment jsp named geoLocations.jsp | Completed
|  |  | 2015-05-20 | 2015-05-21 | Swapnil | Add the tabs in the main jsp. On click of this particular tab, create an ajax method which will call the above created controller method and retrieve and populate all the data in the jsp. | Completed
|  |  | 2015-05-25 | 2015-05-26 | Swarnima/Swapnil | Test and fix the weather code. | In progress
|  |  | 2015-05-26 | 2015-05-29 | Swarnima/Swapnil | Integrate the HTML for orders dashboard.

## IOS Dev
S.No | Task description | Effort (days) | Start Date | End Date | Owner | Comments/Assumptions | Status
0 | Set up the Hybris | 0 |  | 2015-05-25 | Mayur | Set up as per document | In Progress
1 | Set up the Use case 2 code "servicecore" zip file in hybris | 1 | 2015-05-25 | 2015-05-26 | Mayur | Set up as per document
2 | The promotions notifications showing on IOS App - The welcome message is coming as heading for the promotions. We need to show the welcome messages separately | 1 | 2015-05-26 | 2015-05-27 | Mayur | Make the welcome message as a separate notification
3 | Regarding the promotions notifications showing on IOS App - On click of the promotions, it is redirecting to HAC as the URL at the back end of the promotions is wrong. We need to remove the url on click of the promotions, Instead we can show the alert type pop-up on click of the promotions, which will show the full promotions message with code and validity | 1 | 2015-05-27 | 2015-05-28 | Mayur
4 | The promotions are only showing when the customer is logged into the IOS App. Need to fix this as it should show the promotions even when the customer is not logged in, as we will be using the device id to recognise the promotions list. | 1 | 2015-05-28 | 2015-05-29 | Mayur
5 | The categories names seems to be hardcoded in the IOS App. It should be dynamic based on the category code | 2 | 2015-06-01 | 2015-06-02 | Mayur
6 | The health products category is not showing on the IOS App. | 0.5 | 2015-06-02 | 2015-06-02 | Mayur | related to the above point
7 | Send the geoLocation data of the user. And show the message and promotions that are returned as the json body of the response | 2 | 2015-06-03 | 2015-06-04 | Mayur | URL : /greetCustomer POST Request Body { "latitude":"12.32", "longitude":"10.23", "customerId":"example@email.com" } Response Body Will update shortly