## Sheet1
S.No | Task description | Effort (days) | Start Date | End Date | Owner | Comments/Assumptions | Status
1 | New module creation (b2c) (name : QRScanner) | 0.5 | 2014-11-03 | 2014-11-03 | All | Download latest Hybris 5.3 and create new b2c module "QRScanner" + Ant clean all + Init + Host files entry | Completed
2 | CSR Login page | 1.5 | 2014-11-03 | 2014-11-03 | Swarnima | Just like BnC , CSR login page implementation is required here ( proper user group needs to be created) | Completed
3 | Addition of CSR Login link on the OOB Header of the storefront | 0.5 | 2014-11-03 | 2014-11-03 | Swapnil | Entry point for CSR to login. Create impex to add this link on the header component. | Completed
4 | Data modeling for new field UCOID | 0.5 | 2014-11-03 | 2014-11-03 | Prasun | Add this new field in Database + Hybris Update | Completed
5 | Data modeling for new itemtype: collectOrder (This will manage the queue for list of orders that needs to be packed and collected from counter) | 0.5 | 2014-11-04 | 2014-11-04 | Prasun | This type will have 5 attributes (1) CID, (2) OID, (3) UCOID, (4) PID, (5) Status. --> CID: Customer Id --> OID: Oder Id --> UCOID: Our new field --> PID: Product Id --> Status: Product collection status (PENDING/COMPLETED) | Completed
6 | Customize OOB Delivery method page and provide option to choose the "Pick up from next counter" option. | 1 | 2014-11-04 | 2014-11-05 | Prasun | Add new filed/drop down for "Pick up from next counter" + Hybris update + UI Changes. Also add a check that UCOID code will be generated (and will be added in queue) only when user has slected this option of delivery else its OOB. | Completed
7 | Utility class for creating UCOID(encrypted unique customer & order identifier [UCOID] on the fly based on order id, customer id, Date and Time of placing Order) | 1.5 | 2014-11-05 | 2014-11-06 | Swarnima | Complete code logic to generate and save UCOID. | Completed
8 | Interceptor class for calling and retrieving the generated UCOID from Utility class and saving the value in Order Model. | 1 | 2014-11-06 | 2014-11-07 | Swarnima |  | Completed
9 | Complete code logic to capture & save the values in "collectOrder" table (i.e. when customer who choose to collect the order places the order and when CSR agent completes the order) | 1 | 2014-11-07 | 2014-11-10 | Prasun | It is through this table the queue for order (that needs to be collected) will be managed by CSR agent, hence it needs to be updated every time with latest values. | Completed
10 | Customize Thank you page to show UCOID along with order details. | 0.5 | 2014-11-07 | 2014-11-07 | Swapnil | If the UCOID is generated than it needs to be shown on Thankyou page. Once the order is marked as complete the message should be promped to the customer to collect the order from the next counter/billing desk. On order confirmation page, UCOID is to be displayed to the customer(along with a message to not share it with anyone.) | Completed
11 | CSR Landing page to show last 5 orders ( configurable) that are pending for package & collection. | 1.5 | 2014-11-07 | 2014-11-10 | Swarnima | This will be CSR page for displaying orders placed (based on delivery Mode : Pick up from next counter) in tabular format(auto-refresh along with a refresh button) | Completed
12 | HTML integration for this CSR Landing page | 1 |  |  | Swapnil/Swarnima | Assuming HTMLs will be provided by UI team.
13 | CSR agent should have option to see all the pending orders, i.e. if more than 5 orders are pending then "Show more" link should be provided that will expand the table to show all pending order ( pagination if required) | 1.5 | 2014-11-11 | 2014-11-12 | Swapnil | Use Hybris OOB pagination feature (if required).
14 | CSR agent should have option to search the pending order details through UCOID. | 1 | 2014-11-12 | 2014-11-13 | Swapnil |  | In Process
15 | The pending order detail page should show all the details of the order & customer | 1.5 | 2014-11-11 | 2014-11-12 | Swarnima | Also on click of UCOID, This order details shall be opened along with status change drop-down (submit on value change). | In Process
16 | After marking the order as complete , the status should change in "collectOrder" table | 1 | 2014-11-12 | 2014-11-13 | Swarnima
17 | After the order is collected it should get removed from the pending order ( by changing the status to complete) | 1 | 2014-11-13 | 2014-11-14 | Swarnima | Order status to be updated on the order confirmation page(auto-refresh along with a refresh button)
18 | On the customer My Account create a Order Collect History page ( similar to OOB Order History page) showing the current staus of the order i.e. Pending or Complete (ready to be collected from counter). | 2 | 2014-11-11 | 2014-11-12 | Prasun |  | In Process